## 1st qtr
FDP Form 7 - 20% Component of the IRA Utilization
20% COMPONENT OF THE IRA UTILIZATION
FOR THE 1st QUARTER, CY 2016
CITY GOVERNMENT OF MALABON
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date
ECONOMIC DEVELOPMENT
Proposed Upgrading / Rehabilitation of various alleys along Langray St. between blk. 14 and 17 including drainage | Brgy. Longos | 2158030.81 | 2016-02-22 | 2016-05-06 | 85% | 1834326.19 |  | on-going
Proposed Upgrading / Rehabilitation of Various Alleys along Dulong Herrera St., including drainage | Brgy. Ibaba | 1300981.66 | 2016-02-22 | 2016-05-21 | 50% | 650490.83 |  | on-going
Proposed Upgrading / Rehabilitation of Alley at Mendiola St. including drainage | Brgy. Tonsuya | 1130479.21 | 2016-02-22 | 2016-05-06 | 100% | 1130479.21 |  | completed
Proposed Upgrading / Rehabilitation of Various Alleys along Halaan St. Blk. 2 Phase II including drainage | Brgy. Longos | 1302928.72 | 2016-02-22 | 2016-04-21 | 85% | 1107489.41 |  | on-going
Proposed Upgrading / Rehabilitation of Interior F. Nicolas St. including drainage | Brgy. Niugan | 1345464.14 | 2016-02-22 | 2016-04-21 | 95% | 1278190.93 |  | on-going
Proposed Upgrading / Rehabilitation of Various Alleys at Jacinto St. including Drainage | Brgy. Concepcion | 2293278.62 | 2016-02-22 | 2016-06-20 | 50% | 1146639.31 |  | on-going
Proposed Upgrading / Rehabilitation of Various Alleys at Sulucan St. including drainage (Phase II) | Brgy. Hulong Duhat | 2797630.37 | 2016-02-22 | 2016-06-20 | 70% | 1958341.25 |  | on-going
Proposed Upgrading / Rehabilitation of Various Alleys along Don Basilio Bautista Blvd. including drainage | Brgy. Hulong Duhat | 1428672.29 | 2016-02-22 | 2016-05-21 | 100% | 1428672.29 |  | completed
Proposed Upgrading / Rehabilitation of Various Alleys at Celia II St. including drainage (Phase II) | Brgy. Bayan-Bayanan | 2868332.67 | 2016-02-22 | 2016-06-20 | 95% | 2724916.04 |  | on-going
Proposed Upgrading / Rehabilitation of Alleys at Blk. 15, 16, and Hasa-Hasa St. portion (Road 45) including drainage | Brgy. Longos | 1769776.72 | 2016-02-22 | 2016-05-21 | 85% | 1504310.21 |  | on-going
Proposed Upgrading / Rehabilitation of Kitang Alley along Labahita St. between Blk. 14,15,16 and 17 including drainage | Brgy. Longos | 1382162.66 | 2016-02-22 | 2016-05-21 | 90% | 1243946.39 |  | on-going
ENVIRONMENTAL MANAGEMENT
Proposed Rehablilitation of Drainage Canal at Karen St. | Brgy. Hulong Duhat | 1558119.17 | 2016-02-22 | 2016-04-06 | 95% | 1480213.21 |  | on-going
Proposed Upgrading / Rehabilitation of Drainage Canal along Asogue St. leading to Tugatog pumping station | Brgy. Tugatog | 634331.32 | 2016-03-04 | 2016-04-17 | 100% | 634331.32 |  | completed
SOCIAL DEVELOPMENT
We hereby certify that we have reviewed the contents and hereby attest to
the veracity and correctness of the data or information contained in this
document.
Prepared by : |  | Reviewed by : |  |  |  | Noted by :
CYNTHIA P. RAMOS |  | ENGR. ALAN A. GATPOLINTAN |  |  |  | HON. ANTOLIN A. ORETA III
City Budget Officer |  | City Engineer |  |  |  | City Mayor