## 2nd qrtr
FDP Form 7 - 20% Component of the IRA Utilization
20% COMPONENT OF THE IRA UTILIZATION
FOR THE 2nd QUARTER, CY 2014
CITY GOVERNMENT OF MALABON
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date
SOCIAL DEVELOPMENT
ECONOMIC DEVELOPMENT
Proposed Upgrading/Rehabilitation of Roads (portion) | San Vicente Village, Barangay Maysilo | 2755776.39 | May 6,2014 | 2014-06-10 | 60% | 1653465.83
Proposed repair/rehabilitation of sidewalks | along Rizal Ave. Ext. (from Gen. Luna / Adante Sts. to F. Sevilla Blvd.) located at Brgys. Tañong and San Agustin | 560667.59 | 2014-05-06 | 2014-06-02 | 100% | 560667.59
Proposed Upgrading/Rehabilitation of Luis St. (Completion) | located at Barangays Panghulo and Santulan | 2321606.58 | 2014-05-06 | 2014-06-17 | 50% | 1160803.29
Proposed Upgrading/Rehabilitation of J. Templora St. | located at Barangay Santulan | 2787246.65 | May 6,2014 | 2014-06-18 | 50% | 1393623.33
ENVIRONMENTAL MANAGEMENT
Proposed Construction of Drainage Line | Malabon City Pound to Don Basilio Bautista Blvd., Barangay Dampalit | 192385.83 | 2014-05-12 | 2014-06-02 | 100% | 192385.83
We hereby certify that we have reviewed the contents and hereby attest to
the veracity and correctness of the data or information contained in this
document.
CYNTHIA P. RAMOS |  |  | HON. ANTOLIN A. ORETA III
City Budget Officer |  |  | City Mayor