## 2nd qtr.
FDP Form 7 - 20% Component of the IRA Utilization
20% COMPONENT OF THE IRA UTILIZATION
FOR THE 2nd QUARTER, CY 2015
CITY GOVERNMENT OF MALABON
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date
SOCIAL DEVELOPMENT
ECONOMIC DEVELOPMENT
Proposed Upgrading/Rehabilitation of Asogue St., including Drainage | Brgy. Tugatog | 3611888.52 | 2015-05-25 | 2015-08-14 | 50% | 1805944.26
Proposed Upgrading/Rehabilitation of Macanas St., including Drainage | Brgy. Panghulo | 4895472.35 | 2015-05-25 | 2015-08-29 | 50% | 2447736.18
ENVIRONMENTAL MANAGEMENT
Proposed Rehabilitation of Drainage Line at Justice Compound beside half court | Brgy. Catmon | 252486 | 2015-05-04 | 2015-05-25 | 100% | 252486
We hereby certify that we have reviewed the contents and hereby attest to
the veracity and correctness of the data or information contained in this
document.
CYNTHIA P. RAMOS |  |  | HON. ANTOLIN A. ORETA III
City Budget Officer |  |  | City Mayor