## 1st qtr
FDP Form 7 - 20% Component of the IRA Utilization
20% COMPONENT OF THE IRA UTILIZATION
FOR THE 1st QUARTER, CY 2016
CITY GOVERNMENT OF MALABON
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date
ECONOMIC DEVELOPMENT
Proposed Upgrading / Rehabilitation of various alleys along Langray St. between blk. 14 and 17 including drainage | Brgy. Longos | 2158030.81 | 2016-02-22 | 2016-05-06 | 85% | 1834326.19 |  | on-going | 1834326.1885 | 0.0015
Proposed Upgrading / Rehabilitation of Various Alleys along Dulong Herrera St., including drainage | Brgy. Ibaba | 1300981.66 | 2016-02-22 | 2016-05-21 | 50% | 650490.83 |  | on-going | 650490.83 | 0
Proposed Upgrading / Rehabilitation of Alley at Mendiola St. including drainage | Brgy. Tonsuya | 1130479.21 | 2016-02-22 | 2016-05-06 | 100% | 1130479.21 |  | completed | 1130479.21 | 0
Proposed Upgrading / Rehabilitation of Various Alleys along Halaan St. Blk. 2 Phase II including drainage | Brgy. Longos | 1302928.72 | 2016-02-22 | 2016-04-21 | 85% | 1107489.41 |  | on-going | 1107489.412 | -0.002
Proposed Upgrading / Rehabilitation of Interior F. Nicolas St. including drainage | Brgy. Niugan | 1345464.14 | 2016-02-22 | 2016-04-21 | 95% | 1278190.93 |  | on-going | 1278190.933 | -0.003
Proposed Upgrading / Rehabilitation of Various Alleys at Jacinto St. including Drainage | Brgy. Concepcion | 2293278.62 | 2016-02-22 | 2016-06-20 | 50% | 1146639.31 |  | on-going | 1146639.31 | 0
Proposed Upgrading / Rehabilitation of Various Alleys at Sulucan St. including drainage (Phase II) | Brgy. Hulong Duhat | 2797630.37 | 2016-02-22 | 2016-06-20 | 70% | 1958341.25 |  | on-going | 1958341.259 | -0.009
Proposed Upgrading / Rehabilitation of Various Alleys along Don Basilio Bautista Blvd. including drainage | Brgy. Hulong Duhat | 1428672.29 | 2016-02-22 | 2016-05-21 | 100% | 1428672.29 |  | completed | 1428672.29 | 0
Proposed Upgrading / Rehabilitation of Various Alleys at Celia II St. including drainage (Phase II) | Brgy. Bayan-Bayanan | 2868332.67 | 2016-02-22 | 2016-06-20 | 95% | 2724916.04 |  | on-going | 2724916.0365 | 0.0035
Proposed Upgrading / Rehabilitation of Alleys at Blk. 15, 16, and Hasa-Hasa St. portion (Road 45) including drainage | Brgy. Longos | 1769776.72 | 2016-02-22 | 2016-05-21 | 85% | 1504310.21 |  | on-going | 1504310.212 | -0.002
Proposed Upgrading / Rehabilitation of Kitang Alley along Labahita St. between Blk. 14,15,16 and 17 including drainage | Brgy. Longos | 1382162.66 | 2016-02-22 | 2016-05-21 | 90% | 1243946.39 |  | on-going | 1243946.394
ENVIRONMENTAL MANAGEMENT
Proposed Rehablilitation of Drainage Canal at Karen St. | Brgy. Hulong Duhat | 1558119.17 | 2016-02-22 | 2016-04-06 | 95% | 1480213.21 |  | on-going | 1480213.2115
Proposed Upgrading / Rehabilitation of Drainage Canal along Asogue St. leading to Tugatog pumping station | Brgy. Tugatog | 634331.32 | 2016-03-04 | 2016-04-17 | 100% | 634331.32 |  | completed | 634331.32
SOCIAL DEVELOPMENT
We hereby certify that we have reviewed the contents and hereby attest to
the veracity and correctness of the data or information contained in this
document.
Prepared by : |  | Reviewed by : |  |  |  | Noted by :
CYNTHIA P. RAMOS |  | ENGR. ALAN A. GATPOLINTAN |  |  |  | HON. ANTOLIN A. ORETA III
City Budget Officer |  | City Engineer |  |  |  | City Mayor

## 2nd qtr
FDP Form 7 - 20% Component of the IRA Utilization
20% COMPONENT OF THE IRA UTILIZATION
FOR THE 2nd QUARTER, CY 2016
CITY GOVERNMENT OF MALABON
| Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[6 empty] | % of Completion | Total Cost Incurred to Date
ECONOMIC DEVELOPMENT
39 | Proposed Upgrading / Rehabilitation of Kitang Alley along Labahita St. between Blk. 14,15,16 and 17 including drainage | Brgy. Longos | 1382162.66 | 2016-02-22 | 2016-05-21 | 100% | 1382162.66 |  | completed | 0 | 1243946.394
41 | Proposed Upgrading / Rehabilitation of Interior F. Nicolas St. including drainage | Brgy. Niugan | 1345464.14 | 2016-02-22 | 2016-04-21 | 100% | 1345464.14 |  | completed | 0 | 1278190.933 | 67273.207
30 | Proposed Upgrading / Rehabilitation of Various Alleys at Celia II St. including drainage (Phase II) | Brgy. Bayan-Bayanan | 2868332.67 | 2016-02-22 | 2016-06-20 | 100% | 2868332.67 |  | completed | 0 | 2724916.0365 | 143416.6335
37 | Proposed Upgrading / Rehabilitation of various alleys along Langaray St. between Blk. 14 and 17 including drainage. | Brgy. Longos | 2158030.81 | 2016-02-22 | 2016-05-06 | 100% | 2158030.81 |  | completed | 0 | 1834326.1885 | 323704.6215
40 | Proposed Upgrading / Rehabilitation of Alleys at Blk. 15, 16, and Hasa-Hasa St. portion (Road 45) including drainage | Brgy. Longos | 1769776.72 | 2016-02-22 | 2016-05-21 | 100% | 1769776.72 |  | completed | 0 | 1504310.212 | 265466.508
38 | Proposed Upgrading / Rehabilitation of Various Alleys along Halaan St. Blk. 2 Phase II including drainage | Brgy. Longos | 1302928.72 | 2016-02-22 | 2016-04-21 | 100% | 1302928.72 |  | completed | 0 | 1107489.412 | 195439.308
35 | Proposed Upgrading / Rehabilitation of Various Alleys along Don Basilio Bautista Blvd. including drainage | Brgy. Hulong Duhat | 1428672.29 | 2016-02-22 | 2016-05-21 | 100% | 1428672.29 |  | completed | 0 | 1428672.29 | 0
31 | Proposed Upgrading / Rehabilitation of Various Alleys at Jacinto St. including Drainage | Brgy. Concepcion | 2293278.62 | 2016-02-26 | 2016-06-24 | 100% | 2293278.62 |  | completed | 0 | 1146639.31 | 1146639.31
34 | Proposed Upgrading / Rehabilitation of Various Alleys at Sulucan St. including drainage (Phase II) | Brgy. Hulong Duhat | 2797630.37 | 2016-02-22 | 2016-06-20 | 100% | 2797630.37 |  | completed | 0 | 1958341.259 | 839289.111
44 | Proposed Upgrading / Rehabilitation of Alley at Mendiola St. including drainage | Brgy. Tonsuya | 1130479.21 | 2016-02-22 | 2016-05-06 | 100% | 1130479.21 |  | completed | 0 | 1130479.21 | 0
36 | Proposed Upgrading / Rehabilitation of Various Alleys along Dulong Herrera St., including drainage | Brgy. Ibaba | 1300981.66 | 2016-02-22 | 2016-05-21 | 100% | 1300981.66 |  | completed | 0 | 650490.83 | 650490.83
56 | Proposed Upgrading / Rehabilitation of Various Alleys at Jacinto St. including drainage (Phase II) | Brgy. Concepcion | 2396322.66 | 2016-03-29 | 2016-06-26 | 100% | 2396322.66 |  | completed, yet to be paid | 0
33 | Proposed Upgrading / Rehabilitation of Alley along A. Gervacio St. including drainage | Brgy. Hulong Duhat | 383642.21 | 2016-03-16 | 2016-04-29 | 100% | 383642.21 |  | completed | 0
49 | Proposed Upgrading / Rehabilitation of Various Alleys along Pampano St. at Blk. 49 | Brgy. Longos | 3536653.78 | 2016-03-29 | 2016-07-26 | 78% | 2758589.9484 |  | 50% paid already, on- going | 778063.8316
50 | Proposed Upgrading / Rehabilitation of Various Alleys along Hito St. Blk.3 including drainage | Brgy. Longos | 1170818.47 | 2016-03-29 | 2016-05-27 | 100% | 1170818.47 |  | completed | 0
51 | Proposed Upgrading / Rehabilitation of Hito St. (Portion) including Drainage | Brgy. Longos | 2318301.28 | 2016-03-29 | 2016-05-27 | 100% | 2318301.28 |  | completed, yet to be paid | 0
32 | Proposed Upgrading / Rehabilitation of Alley at Escanilla St. (Portion) including drainage | Brgy. Concepcion | 291566.37 | 2016-03-16 | 2016-04-29 | 100% | 291566.37 |  | completed | 0
29 | Proposed Upgrading / Rehabilitation of Various Alleys at Javier II (Phase II) including drainage | Brgy. Baritan | 2448854.58 | 2016-02-22 | 2016-05-21 | 100% | 2448854.58 |  | completed | 0
57 | Proposed Upgrading / Rehabilitation of Alley along Hiwas St. Blk 10 Phase 2 | Brgy. Longos | 243122.96 | 2016-05-29 | 2016-04-27 | 100% | 243122.96 |  | completed | 0
53 | Proposed Upgrading / Rehabilitation of Cristina St. (Portion) including Drainage | Brgy. Panghulo | 719714.1 | 2016-03-29 | 2016-05-12 | 100% | 719714.1 |  | completed | 0
54 | Proposed Rehabilitation of Duhat Road (Portion) including Drainage | Brgy. Potrero | 2717037.77 | 2016-03-29 | 2016-05-27 | 100% | 2717037.77 |  | completed | 0
43 | Proposed Upgrading / Rehabilitation of Various Alleys along Custodio St. including drainage (Phase II) | Brgy. Santulan | 2142344.3 | 2016-02-22 | 2016-05-21 | 100% | 2142344.3 |  | completed | 0
55 | Proposed Reblocking of Custodio St. and Mabolo St. | Brgy. Santulan | 3715108.67 | 2016-03-29 | 2016-06-26 | 100% | 3715108.67 |  | completed | 0
42 | Proposed Upgrading / Rehabilitation of Various Alleys along J.M. Templora St. including drainage | Brgy. Santulan | 629036.5 | 2016-03-04 | 2016-05-02 | 100% | 629036.5 |  | completed | 0
47 | Proposed Upgrading / Rehabilitation of Aluminio St. (Portion) including drainage | Brgy. Tugatog | 3335428.85 | 2016-03-29 | 2016-06-26 | 100% | 3335428.85 |  | 50% paid already, 50% yet to be paid | 0
46 | Proposed Upgrading / Rehabilitation of Estanio St. (Portion) including drainage | Brgy. Tugatog | 2108660.17 | 2016-03-29 | 2016-06-11 | 100% | 2108660.17 |  | completed, yet to be paid | 0
45 | Proposed Upgrading / Rehabilitation of Plata St. (Portion) including drainage | Brgy. Tugatog | 901498.18 | 2016-03-29 | 2016-05-12 | 100% | 901498.18 |  | completed | 0
48 | Proposed Rehabilitation of Sanchez St. (Portion) including drainage | Brgy. Tinajeros | 4990609.13 | 2016-03-29 | 2016-06-26 | 50% | 2495304.565 |  | 50% completed, 50% yet to be paid, on-going | 2495304.565
62 | Proposed Upgrading / Rehabilitation of Various Alley along Maya-Maya St. at Blk. 50 including drainage (Phase II) | Brgy. Longos | 195935.05 | 2016-05-17 | 2016-06-15 | 100% | 195935.05 |  | completed | 0
58 | Proposed Upgrading / Rehabilitation of Alupihang Dagat (Portion) including drainage | Brgy. Longos | 2225434.41 | 2016-05-17 | 2016-07-15 | 100% | 2225434.41 |  | completed | 0
52 | Proposed Upgrading / Rehabilitation of Various Alley along Hiwas St. at Blk. 8 and 9 including drainage | Brgy. Longos | 1749877.16 | 2016-05-17 | 2016-07-30 | 59% | 1032427.5244 |  | 59% completed, yet to be paid, on-going | 717449.6356
SOCIAL DEVELOPMENT
1 | Proposed Installation of Five (5) Sets of Streetlights along Paez Street | Brgy. Concepcion | 508994.27 | 2016-03-29 | 2016-04-27 | 100% | 508994.27 |  | completed | 0
16 | Proposed Construction of Potrero Multi-Purpose Hall located at Camachile St. | Brgy. Potrero | 3744743.1 | 2016-02-22 | 2016-05-21 | 100% | 3744743.1 |  | completed | 0
2 | Proposed Rehabilitation of Streetlights at Various Streets in Various Brgy. City of Malabon | Various Brgy. | 1768581 | 2016-03-22 | 2016-05-30 | 100% | 1768581 |  | completed | 0
15 | Proposed Rehabilitation of Manpower Development Centre (Laboratory) at CMPI located at Gov. Pascual Ave., corner A. Reyes St., | Brgy. Baritan | 175516.97 | 2016-05-17 | 2016-05-31 | 100% | 175516.97 |  | completed | 0
ENVIRONMENTAL MANAGEMENT
72 | Proposed Upgrading / Rehabilitation of Drainage Canal along Asogue St. leading to Tugatog pumping station | Brgy. Tugatog | 634331.32 | 2016-03-04 | 2016-04-17 | 100% | 634331.32 |  | completed | 0 | 634331.32
73 | Proposed Rehablilitation of Drainage Canal at Karen St. | Brgy. Hulong Duhat | 1558119.17 | 2016-02-22 | 2016-04-06 | 100% | 1558119.17 |  | completed | 0 | 1480213.2115
68 | Proposed Installation of Garbage Trash Trap at Spine Canal along Lapu-Lapu Avenue | Brgy. Longos | 286090.58 | 2016-03-16 | 2016-04-29 | 100% | 286090.58 |  | completed | 0
| Prepared by : |  | Reviewed by: |  |  |  | Noted by :
| CYNTHIA P. RAMOS |  | ENGR. ALAN A. GATPOLINTAN |  |  |  | HON. ANTOLIN A. ORETA III
| City Budget Officer |  | City Engineer |  |  |  | City Mayor
Note on B26: USER70:
Note on B33: USER70:
Note on B40: USER70:
Note on B48: USER70:
Note on B56: USER70:

## 3rd qtr
FDP Form 7 - 20% Component of the IRA Utilization
20% COMPONENT OF THE IRA UTILIZATION
FOR THE 3rd QUARTER, CY 2016
CITY GOVERNMENT OF MALABON
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date
ECONOMIC DEVELOPMENT
Proposed Upgrading / Rehabilitation of Kitang Alley along Labahita St. between Blk. 14,15,16 and 17 including drainage | Brgy. Longos | 1382162.66 | 2016-02-22 | 2016-05-21 | 100% | 1382162.66 |  | completed | 0 | 1243946.394
Proposed Upgrading / Rehabilitation of Interior F. Nicolas St. including drainage | Brgy. Niugan | 1345464.14 | 2016-02-22 | 2016-04-21 | 100% | 1345464.14 |  | completed | 0 | 1278190.933 | 67273.207
Proposed Upgrading / Rehabilitation of Various Alleys at Celia II St. including drainage (Phase II) | Brgy. Bayan-Bayanan | 2868332.67 | 2016-02-22 | 2016-06-20 | 100% | 2868332.67 |  | completed | 0 | 2724916.0365 | 143416.6335
Proposed Upgrading / Rehabilitation of various alleys along Langaray St. between Blk. 14 and 17 including drainage. | Brgy. Longos | 2158030.81 | 2016-02-22 | 2016-05-06 | 100% | 2158030.81 |  | completed | 0 | 1834326.1885 | 323704.6215
Proposed Upgrading / Rehabilitation of Alleys at Blk. 15, 16, and Hasa-Hasa St. portion (Road 45) including drainage | Brgy. Longos | 1769776.72 | 2016-02-22 | 2016-05-21 | 100% | 1769776.72 |  | completed | 0 | 1504310.212 | 265466.508
Proposed Upgrading / Rehabilitation of Various Alleys along Halaan St. Blk. 2 Phase II including drainage | Brgy. Longos | 1302928.72 | 2016-02-22 | 2016-04-21 | 100% | 1302928.72 |  | completed | 0 | 1107489.412 | 195439.308
Proposed Upgrading / Rehabilitation of Various Alleys along Don Basilio Bautista Blvd. including drainage | Brgy. Hulong Duhat | 1428672.29 | 2016-02-22 | 2016-05-21 | 100% | 1428672.29 |  | completed | 0 | 1428672.29 | 0
Proposed Upgrading / Rehabilitation of Various Alleys at Jacinto St. including Drainage | Brgy. Concepcion | 2293278.62 | 2016-02-22 | 2016-06-20 | 100% | 2293278.62 |  | completed | 0 | 1146639.31 | 1146639.31
Proposed Upgrading / Rehabilitation of Various Alleys at Sulucan St. including drainage (Phase II) | Brgy. Hulong Duhat | 2797630.37 | 2016-02-22 | 2016-06-20 | 100% | 2797630.37 |  | completed | 0 | 1958341.259 | 839289.111
Proposed Upgrading / Rehabilitation of Alley at Mendiola St. including drainage | Brgy. Tonsuya | 1130479.21 | 2016-02-22 | 2016-05-06 | 100% | 1130479.21 |  | completed | 0 | 1130479.21 | 0
Proposed Upgrading / Rehabilitation of Various Alleys along Dulong Herrera St., including drainage | Brgy. Ibaba | 1300981.66 | 2016-02-22 | 2016-05-21 | 100% | 1300981.66 |  | completed | 0 | 650490.83 | 650490.83
Proposed Upgrading / Rehabilitation of Various Alleys at Jacinto St. including drainage (Phase II) | Brgy. Concepcion | 2396322.66 | [6 empty] | 2396322.66
Proposed Upgrading / Rehabilitation of Alley along A. Gervacio St. including drainage | Brgy. Hulong Duhat | 383642.21 |  |  | 100% | 383642.21 |  | completed | 0
Proposed Upgrading / Rehabilitation of Various Alleys along Pampano St. at Blk. 49 | Brgy. Longos | 3536653.78 |  |  | 50% | 1768326.89 |  | on going | 1768326.89
Proposed Upgrading / Rehabilitation of Various Alleys along Hito St. Blk.3 including drainage | Brgy. Longos | 1170818.47 |  |  | 100% | 1170818.47 |  | completed | 0
Proposed Upgrading / Rehabilitation of Hito St. (Portion) including Drainage | Brgy. Longos | 2318301.28 | [6 empty] | 2318301.28
Proposed Upgrading / Rehabilitation of Alley at Escanilla St. (Portion) including drainage | Brgy. Concepcion | 291566.37 |  |  | 100% | 291566.37 |  | completed | 0
Proposed Upgrading / Rehabilitation of Various Alleys at Javier II (Phase II) including drainage | Brgy. Baritan | 2448854.58 |  |  | 100% | 2448854.58 |  | completed | 0
Proposed Upgrading / Rehabilitation of Alley along Hiwas St. Blk 10 Phase 2 | Brgy. Longos | 243122.96 |  |  | 100% | 243122.96 |  | completed | 0
Proposed Upgrading / Rehabilitation of Cristina St. (Portion) including Drainage | Brgy. Panghulo | 719714.1 |  |  | 100% | 719714.1 |  | completed | 0
Proposed Rehabilitation of Duhat Road (Portion) including Drainage | Brgy. Potrero | 2717037.77 |  |  | 100% | 2717037.77 |  | completed | 0
Proposed Upgrading / Rehabilitation of Various Alleys along Custodio St. including drainage (Phase II) | Brgy. Santulan | 2142344.3 |  |  | 100% | 2142344.3 |  | completed | 0
Proposed Reblocking of Custodio St. and Mabolo St. | Brgy. Santulan | 3715108.67 |  |  | 100% | 3715108.67 |  | completed | 0
Proposed Upgrading / Rehabilitation of Various Alleys along J.M. Templora St. including drainage | Brgy. Santulan | 629036.5 |  |  | 100% | 629036.5 |  | completed | 0
Proposed Upgrading / Rehabilitation of Aluminio St. (Portion) including drainage | Brgy. Tugatog | 3335428.85 |  |  | 50% | 1667714.425 |  | on going | 1667714.425
Proposed Upgrading / Rehabilitation of Estanio St. (Portion) including drainage | Brgy. Tugatog | 2108660.17 | [6 empty] | 2108660.17
Proposed Upgrading / Rehabilitation of Plata St. (Portion) including drainage | Brgy. Tugatog | 901498.18 |  |  | 100% | 901498.18 |  | completed | 0
Proposed Rehabilitation of Sanchez St. (Portion) including drainage | Brgy. Tinajeros | 4990609.13 | [6 empty] | 4990609.13
Proposed Upgrading / Rehabilitation of Various Alley along Maya-Maya St. at Blk. 50 including drainage (Phase II) | Brgy. Longos | 195935.05 |  |  | 100% | 195935.05 |  | completed | 0
Proposed Upgrading / Rehabilitation of Alupihang Dagat (Portion) including drainage | Brgy. Longos | 2225434.41 |  |  | 100% | 2225434.41 |  | completed | 0
Proposed Upgrading / Rehabilitation of Various Alley along Hiwas St. at Blk. 8 and 9 including drainage | Brgy. Longos | 1749877.16 | [6 empty] | 1749877.16
SOCIAL DEVELOPMENT
Proposed Installation of Five (5) Sets of Streetlights along Paez Street | Brgy. Concepcion | 508994.27 |  |  | 100% | 508994.27 |  | completed | 0
Proposed Construction of Potrero Multi-Purpose Hall located at Camachile St. | Brgy. Potrero | 3744743.1 |  |  | 100% | 3744743.1 |  | completed | 0
Proposed Rehabilitation of Streetlights at Various Streets in Various Brgy. City of Malabon | Various Brgy. | 1768581 |  |  | 100% | 1768581 |  | completed | 0
Proposed Rehabilitation of Manpower Development Centre (Laboratory) at CMPI located at Gov. Pascual Ave., corner A. Reyes St., | Brgy. Baritan | 175516.97 |  |  | 100% | 175516.97 |  | completed | 0
ENVIRONMENTAL MANAGEMENT
Proposed Upgrading / Rehabilitation of Drainage Canal along Asogue St. leading to Tugatog pumping station | Brgy. Tugatog | 634331.32 | 2016-03-04 | 2016-04-17 | 100% | 634331.32 |  | completed | 0 | 634331.32
Proposed Rehablilitation of Drainage Canal at Karen St. | Brgy. Hulong Duhat | 1558119.17 | 2016-02-22 | 2016-04-06 | 100% | 1558119.17 |  | completed | 0 | 1480213.2115
Proposed Installation of Garbage Trash Trap at Spine Canal along Lapu-Lapu Avenue | Brgy. Longos | 286090.58 |  |  | 100% | 286090.58 |  | completed | 0
Prepared by : |  | Reviewed by : |  |  |  | Noted by :
CYNTHIA P. RAMOS |  | ENGR. ALAN A. GATPOLINTAN |  |  |  | HON. ANTOLIN A. ORETA III
City Budget Officer |  | City Engineer |  |  |  | City Mayor
Note on A26: USER70:
Note on A33: USER70:
Note on A40: USER70:
Note on A48: USER70:
Note on A56: USER70:

## Sheet2
FDP Form 7 - 20% Component of the IRA Utilization
20% COMPONENT OF THE IRA UTILIZATION
FOR THE 2nd QUARTER, CY 2016
CITY GOVERNMENT OF MALABON
| Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[6 empty] | % of Completion | Total Cost Incurred to Date
ECONOMIC DEVELOPMENT
1 | Proposed Upgrading / Rehabilitation of Kitang Alley along Labahita St. between Blk. 14,15,16 and 17 including drainage | Brgy. Longos | 1382162.66 | 2016-02-22 | 2016-05-21 | 90% | 1243946.39 |  | on-going | 1243946.394
2 | Proposed Upgrading / Rehabilitation of Interior F. Nicolas St. including drainage | Brgy. Niugan | 1345464.14 | 2016-02-22 | 2016-04-21 | 95% | 1278190.93 |  | on-going | 1278190.933 | -0.003
3 | Proposed Upgrading / Rehabilitation of Various Alleys at Celia II St. including drainage (Phase II) | Brgy. Bayan-Bayanan | 2868332.67 | 2016-02-22 | 2016-06-20 | 95% | 2724916.04 |  | on-going | 2724916.0365 | 0.0035
4 | Proposed Upgrading / Rehabilitation of various alleys along Langray St. between Blk. 14 and 17 including drainage. | Brgy. Longos | 2158030.81 | 2016-02-22 | 2016-05-06 | 85% | 1834326.19 |  | on-going | 1834326.1885 | 0.0015
5 | Proposed Upgrading / Rehabilitation of Alleys at Blk. 15, 16, and Hasa-Hasa St. portion (Road 45) including drainage | Brgy. Longos | 1769776.72 | 2016-02-22 | 2016-05-21 | 85% | 1504310.21 |  | on-going | 1504310.212 | -0.002
6 | Proposed Upgrading / Rehabilitation of Various Alleys along Halaan St. Blk. 2 Phase II including drainage | Brgy. Longos | 1302928.72 | 2016-02-22 | 2016-04-21 | 85% | 1107489.41 |  | on-going | 1107489.412 | -0.002
7 | Proposed Upgrading / Rehabilitation of Various Alleys along Don Basilio Bautista Blvd. including drainage | Brgy. Hulong Duhat | 1428672.29 | 2016-02-22 | 2016-05-21 | 100% | 1428672.29 |  | completed | 1428672.29 | 0
8 | Proposed Upgrading / Rehabilitation of Various Alleys at Jacinto St. including Drainage | Brgy. Concepcion | 2293278.62 | 2016-02-22 | 2016-06-20 | 50% | 1146639.31 |  | on-going | 1146639.31 | 0
9 | Proposed Upgrading / Rehabilitation of Various Alleys at Sulucan St. including drainage (Phase II) | Brgy. Hulong Duhat | 2797630.37 | 2016-02-22 | 2016-06-20 | 70% | 1958341.25 |  | on-going | 1958341.259 | -0.009
10 | Proposed Upgrading / Rehabilitation of Alley at Mendiola St. including drainage | Brgy. Tonsuya | 1130479.21 | 2016-02-22 | 2016-05-06 | 100% | 1130479.21 |  | completed | 1130479.21 | 0
11 | Proposed Upgrading / Rehabilitation of Various Alleys along Dulong Herrera St., including drainage | Brgy. Ibaba | 1300981.66 | 2016-02-22 | 2016-05-21 | 50% | 650490.83 |  | on-going | 650490.83 | 0
| Proposed Upgrading / Rehabilitation of Various Alleys at Jacinto St. including drainage (Phase II) | Brgy. Concepcion | 2396322.66
| Proposed Upgrading / Rehabilitation of Alley along A. Gervacio St. including drainage | Brgy. Hulong Duhat | 383642.21
| Proposed Upgrading / Rehabilitation of Various Alleys along Pampano St. at Blk. 49 | Brgy. Longos | 3536653.78
| Proposed Upgrading / Rehabilitation of Various Alleys along Hito St. Blk.3 including drainage | Brgy. Longos | 1170818.47
| Proposed Upgrading / Rehabilitation of Hito St. (Portion) including Drainage | Brgy. Longos | 2318301.28
| Proposed Upgrading / Rehabilitation of Alley at Escanilla St. (Portion) including drainage | Brgy. Concepcion | 291566.37
| Proposed Upgrading / Rehabilitation of Various Alleys at Javier II (Phase II) including drainage | Brgy. Baritan | 2448854.58
| Proposed Upgrading / Rehabilitation of Alley along Hiwas St. Blk 10 Phase 2 | Brgy. Longos | 243122.96
| Proposed Upgrading / Rehabilitation of Cristina St. (Portion) including Drainage | Brgy. Panghulo | 719714.1
| Proposed Rehabilitation of Duhat Road (Portion) including Drainage | Brgy. Potrero | 2717037.77
| Proposed Upgrading / Rehabilitation of Various Alleys along Custodio St. including drainage (Phase II) | Brgy. Santulan | 2142344.3
| Proposed Reblocking of Custodio St. and Mabolo St. | Brgy. Santulan | 3715108.67
| Proposed Upgrading / Rehabilitation of Various Alleys along J.M. Templora St. including drainage | Brgy. Santulan | 629036.5
| Proposed Upgrading / Rehabilitation of Aluminio St. (Portion) including drainage | Brgy. Tugatog | 3335428.85
| Proposed Upgrading / Rehabilitation of Estanio St. (Portion) including drainage | Brgy. Tugatog | 2108660.17
| Proposed Upgrading / Rehabilitation of Plata St. (Portion) including drainage | Brgy. Tugatog | 901498.18
| Proposed Rehabilitation of Sanchez St. (Portion) including drainage | Brgy. Tinajeros | 4990609.13
| Proposed Upgrading / Rehabilitation of Various Alley along Maya-Maya St. at Blk. 50 including drainage (Phase II) | Brgy. Longos | 195935.05
| Proposed Upgrading / Rehabilitation of Alupihang Dagat (Portion) including drainage | Brgy. Longos | 2225434.41
| Proposed Upgrading / Rehabilitation of Various Alley along Hiwas St. at Blk. 8 and 9 including drainage | Brgy. Longos | 1749877.16
57997704.47
SOCIAL DEVELOPMENT
| Proposed Installation of Five (5) Sets of Streetlights along Paez St. located at Paez Street | Brgy. Concepcion | 508994.27
| Proposed Construction of Potrero Multi-Purpose Hall located at Camachile St. | Brgy. Potrero | 3744743.1
| Proposed Rehabilitation of Streetlights at Various Streets in Various Brgy. City of Malabon | Various Brgy. | 1768581
| Proposed Rehabilitation of Manpower Development Centre (Laboratory) at CMPI located at Gov. Pascual Ave., corner A. Reyes St., | Brgy. Baritan | 175516.97
6197835.34
ENVIRONMENTAL MANAGEMENT
| Proposed Upgrading / Rehabilitation of Drainage Canal along Asogue St. leading to Tugatog pumping station | Brgy. Tugatog | 634331.32 | 2016-03-04 | 2016-04-17 | 100% | 634331.32 |  | completed | 634331.32
| Proposed Rehablilitation of Drainage Canal at Karen St. | Brgy. Hulong Duhat | 1558119.17 | 2016-02-22 | 2016-04-06 | 95% | 1480213.21 |  | on-going | 1480213.2115
| Proposed Installation of Garbage Trash Trap at Spine Canal along Lapu-Lapu Avenue | Brgy. Longos | 286090.58
2478541.07
66674080.88
| Prepared by : |  | Reviewed by : |  |  |  | Noted by :
| CYNTHIA P. RAMOS |  | ENGR. ALAN A. GATPOLINTAN |  |  |  | HON. ANTOLIN A. ORETA III
| City Budget Officer |  | City Engineer |  |  |  | City Mayor
Note on B26: USER70:
Note on B33: USER70:
Note on B40: USER70:
Note on B48: USER70:
Note on B56: USER70:

## Sheet3
FDP Form 7 - 20% Component of the IRA Utilization
20% COMPONENT OF THE IRA UTILIZATION
FOR THE 2nd QUARTER, CY 2016
CITY GOVERNMENT OF MALABON
| Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[6 empty] | % of Completion | Total Cost Incurred to Date
ECONOMIC DEVELOPMENT
39 | Proposed Upgrading / Rehabilitation of Kitang Alley along Labahita St. between Blk. 14,15,16 and 17 including drainage | Brgy. Longos | 1382162.66 | 2016-02-22 | 2016-05-21 | 100% | 1382162.66 |  | completed | 0 | 1243946.394
41 | Proposed Upgrading / Rehabilitation of Interior F. Nicolas St. including drainage | Brgy. Niugan | 1345464.14 | 2016-02-22 | 2016-04-21 | 100% | 1345464.14 |  | completed | 0 | 1278190.933 | 67273.207
30 | Proposed Upgrading / Rehabilitation of Various Alleys at Celia II St. including drainage (Phase II) | Brgy. Bayan-Bayanan | 2868332.67 | 2016-02-22 | 2016-06-20 | 100% | 2868332.67 |  | completed | 0 | 2724916.0365 | 143416.6335
37 | Proposed Upgrading / Rehabilitation of various alleys along Langaray St. between Blk. 14 and 17 including drainage. | Brgy. Longos | 2158030.81 | 2016-02-22 | 2016-05-06 | 100% | 2158030.81 |  | completed | 0 | 1834326.1885 | 323704.6215
40 | Proposed Upgrading / Rehabilitation of Alleys at Blk. 15, 16, and Hasa-Hasa St. portion (Road 45) including drainage | Brgy. Longos | 1769776.72 | 2016-02-22 | 2016-05-21 | 100% | 1769776.72 |  | completed | 0 | 1504310.212 | 265466.508
38 | Proposed Upgrading / Rehabilitation of Various Alleys along Halaan St. Blk. 2 Phase II including drainage | Brgy. Longos | 1302928.72 | 2016-02-22 | 2016-04-21 | 100% | 1302928.72 |  | completed | 0 | 1107489.412 | 195439.308
35 | Proposed Upgrading / Rehabilitation of Various Alleys along Don Basilio Bautista Blvd. including drainage | Brgy. Hulong Duhat | 1428672.29 | 2016-02-22 | 2016-05-21 | 100% | 1428672.29 |  | completed | 0 | 1428672.29 | 0
31 | Proposed Upgrading / Rehabilitation of Various Alleys at Jacinto St. including Drainage | Brgy. Concepcion | 2293278.62 | 2016-02-22 | 2016-06-20 | 100% | 2293278.62 |  | completed | 0 | 1146639.31 | 1146639.31
34 | Proposed Upgrading / Rehabilitation of Various Alleys at Sulucan St. including drainage (Phase II) | Brgy. Hulong Duhat | 2797630.37 | 2016-02-22 | 2016-06-20 | 100% | 2797630.37 |  | completed | 0 | 1958341.259 | 839289.111
44 | Proposed Upgrading / Rehabilitation of Alley at Mendiola St. including drainage | Brgy. Tonsuya | 1130479.21 | 2016-02-22 | 2016-05-06 | 100% | 1130479.21 |  | completed | 0 | 1130479.21 | 0
36 | Proposed Upgrading / Rehabilitation of Various Alleys along Dulong Herrera St., including drainage | Brgy. Ibaba | 1300981.66 | 2016-02-22 | 2016-05-21 | 100% | 1300981.66 |  | completed | 0 | 650490.83 | 650490.83
56 | Proposed Upgrading / Rehabilitation of Various Alleys at Jacinto St. including drainage (Phase II) | Brgy. Concepcion | 2396322.66 | [6 empty] | 2396322.66
33 | Proposed Upgrading / Rehabilitation of Alley along A. Gervacio St. including drainage | Brgy. Hulong Duhat | 383642.21 |  |  | 100% | 383642.21 |  | completed | 0
49 | Proposed Upgrading / Rehabilitation of Various Alleys along Pampano St. at Blk. 49 | Brgy. Longos | 3536653.78 |  |  | 50% | 1768326.89 |  | on going | 1768326.89
50 | Proposed Upgrading / Rehabilitation of Various Alleys along Hito St. Blk.3 including drainage | Brgy. Longos | 1170818.47 |  |  | 100% | 1170818.47 |  | completed | 0
51 | Proposed Upgrading / Rehabilitation of Hito St. (Portion) including Drainage | Brgy. Longos | 2318301.28 | [6 empty] | 2318301.28
32 | Proposed Upgrading / Rehabilitation of Alley at Escanilla St. (Portion) including drainage | Brgy. Concepcion | 291566.37 |  |  | 100% | 291566.37 |  | completed | 0
29 | Proposed Upgrading / Rehabilitation of Various Alleys at Javier II (Phase II) including drainage | Brgy. Baritan | 2448854.58 |  |  | 100% | 2448854.58 |  | completed | 0
57 | Proposed Upgrading / Rehabilitation of Alley along Hiwas St. Blk 10 Phase 2 | Brgy. Longos | 243122.96 |  |  | 100% | 243122.96 |  | completed | 0
53 | Proposed Upgrading / Rehabilitation of Cristina St. (Portion) including Drainage | Brgy. Panghulo | 719714.1 |  |  | 100% | 719714.1 |  | completed | 0
54 | Proposed Rehabilitation of Duhat Road (Portion) including Drainage | Brgy. Potrero | 2717037.77 |  |  | 100% | 2717037.77 |  | completed | 0
43 | Proposed Upgrading / Rehabilitation of Various Alleys along Custodio St. including drainage (Phase II) | Brgy. Santulan | 2142344.3 |  |  | 100% | 2142344.3 |  | completed | 0
55 | Proposed Reblocking of Custodio St. and Mabolo St. | Brgy. Santulan | 3715108.67 |  |  | 100% | 3715108.67 |  | completed | 0
42 | Proposed Upgrading / Rehabilitation of Various Alleys along J.M. Templora St. including drainage | Brgy. Santulan | 629036.5 |  |  | 100% | 629036.5 |  | completed | 0
47 | Proposed Upgrading / Rehabilitation of Aluminio St. (Portion) including drainage | Brgy. Tugatog | 3335428.85 |  |  | 50% | 1667714.425 |  | on going | 1667714.425
46 | Proposed Upgrading / Rehabilitation of Estanio St. (Portion) including drainage | Brgy. Tugatog | 2108660.17 | [6 empty] | 2108660.17
45 | Proposed Upgrading / Rehabilitation of Plata St. (Portion) including drainage | Brgy. Tugatog | 901498.18 |  |  | 100% | 901498.18 |  | completed | 0
48 | Proposed Rehabilitation of Sanchez St. (Portion) including drainage | Brgy. Tinajeros | 4990609.13 | [6 empty] | 4990609.13
62 | Proposed Upgrading / Rehabilitation of Various Alley along Maya-Maya St. at Blk. 50 including drainage (Phase II) | Brgy. Longos | 195935.05 |  |  | 100% | 195935.05 |  | completed | 0
58 | Proposed Upgrading / Rehabilitation of Alupihang Dagat (Portion) including drainage | Brgy. Longos | 2225434.41 |  |  | 100% | 2225434.41 |  | completed | 0
52 | Proposed Upgrading / Rehabilitation of Various Alley along Hiwas St. at Blk. 8 and 9 including drainage | Brgy. Longos | 1749877.16 | [6 empty] | 1749877.16
SOCIAL DEVELOPMENT
1 | Proposed Installation of Five (5) Sets of Streetlights along Paez Street | Brgy. Concepcion | 508994.27 |  |  | 100% | 508994.27 |  | completed | 0
16 | Proposed Construction of Potrero Multi-Purpose Hall located at Camachile St. | Brgy. Potrero | 3744743.1 |  |  | 100% | 3744743.1 |  | completed | 0
2 | Proposed Rehabilitation of Streetlights at Various Streets in Various Brgy. City of Malabon | Various Brgy. | 1768581 |  |  | 100% | 1768581 |  | completed | 0
15 | Proposed Rehabilitation of Manpower Development Centre (Laboratory) at CMPI located at Gov. Pascual Ave., corner A. Reyes St., | Brgy. Baritan | 175516.97 |  |  | 100% | 175516.97 |  | completed | 0
ENVIRONMENTAL MANAGEMENT
72 | Proposed Upgrading / Rehabilitation of Drainage Canal along Asogue St. leading to Tugatog pumping station | Brgy. Tugatog | 634331.32 | 2016-03-04 | 2016-04-17 | 100% | 634331.32 |  | completed | 0 | 634331.32
73 | Proposed Rehablilitation of Drainage Canal at Karen St. | Brgy. Hulong Duhat | 1558119.17 | 2016-02-22 | 2016-04-06 | 100% | 1558119.17 |  | completed | 0 | 1480213.2115
68 | Proposed Installation of Garbage Trash Trap at Spine Canal along Lapu-Lapu Avenue | Brgy. Longos | 286090.58 |  |  | 100% | 286090.58 |  | completed | 0
| Prepared by : |  | Reviewed by : |  |  |  | Noted by :
| CYNTHIA P. RAMOS |  | ENGR. ALAN A. GATPOLINTAN |  |  |  | HON. ANTOLIN A. ORETA III
| City Budget Officer |  | City Engineer |  |  |  | City Mayor
Note on B26: USER70:
Note on B33: USER70:
Note on B40: USER70:
Note on B48: USER70:
Note on B56: USER70: