## 3rd qtr
FDP Form 7 - 20% Component of the IRA Utilization
20% COMPONENT OF THE IRA UTILIZATION
FOR THE 3rd QUARTER, CY 2015
CITY GOVERNMENT OF MALABON
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date
ECONOMIC DEVELOPMENT
Proposed Upgrading/Rehabilitation of Asogue St., including Drainage | Tugatog | 3611888.52 | 2015-06-01 | 2015-08-14 | 100% | 3611888.52 |  | 50% billing paid
Proposed Upgrading/Rehabilitation of Macanas St., including Drainage | Panghulo | 4895472.35 | 2015-06-01 | 2015-08-29 | 100% | 4895472.35 |  | 100% billing paid
Proposed Upgrading/Rehabilitation of Alley at Bantayan including Drainage located along Don Baslio Bautista Blvd. (Phase II) | Hulong Duhat | 628970.95 | 2015-06-01 | 2015-07-15 | 100% | 628970.95 |  | 100% billing paid
Proposed Re-blocking of Basilio St. (Portion) | Acacia | 2007558.18 | 2015-06-01 | 2015-07-15 | 100% | 2007558.18 |  | 100% billing paid
Proposed Upgrading/Rehabilitation of Alley at Block-11, Hasa-Hasa St. | Longos | 420693.59 | 2015-06-01 | 2015-07-15 | 100% | 420693.59 |  | 100% billing paid
Proposed Upgrading/Rehabilitation of Herrera St., including Drainage | Ibaba | 2342186.14 | 2015-06-01 | 2015-08-29 | 100% | 2342186.14 |  | 100% billing paid
Proposed Upgrading/Rehabilitation of Pescador I and II including Drainage along T. Santos St. | Baritan | 504524.49 | 2015-06-01 | 2015-07-15 | 100% | 504524.49 |  | 100% billing paid
Proposed Repair and Rehabilitation of Alley 1 along J.M. Templora St. including Drainage | Santulan | 2437182.53 | 2015-06-17 | 2015-08-15 | 100% | 2437182.53 |  | 100% billing paid
Proposed Upgrading/Rehabilitation of Alleys between Manapat, Adante and Rivera Streets | Tañong | 1421549.17 | 2015-06-17 | 2015-08-15 | 100% | 1421549.17 |  | 100% billing paid
Proposed Upgrading/Rehabilitation of Escanilla St., (portion) and Alley including Drainage | Concepcion | 1972549.23 | 2015-06-17 | 2015-08-15 | 100% | 1972549.23 |  | 100% billing paid
Proposed Upgrading/Rehabilitation of Burgos St.,(portion) and alleys including Drainage | Concepcion | 2466613.93 | 2015-06-17 | 2015-08-30 | 100% | 2466613.93 |  | 50% billing paid
Proposed Upgrading/Rehabilitation of Alleys at Javier II St., Including Drainage | Baritan | 2029323.88 | 2015-06-17 | 2015-08-15 | 100% | 2029323.88 |  | 100% billing paid
Proposed Upgrading/Rehabilitation of Alleys along Custodio St., including Drainage | Santulan | 1553043.59 | 2015-06-17 | 2015-08-15 | 100% | 1553043.59 |  | 100% billing paid
Proposed Upgrading/Rehabilitation of Paez St., including Drainage | Concepcion | 3053748.51 | 2015-06-17 | 2015-08-30 | 100% | 3053748.51 |  | 100% billing paid
Proposed Upgrading/Rehabilitation of Alley at Celia II including Drainage | Bayan-Bayanan | 1493712.97 | 2015-06-17 | 2015-08-15 | 100% | 1493712.97 |  | 100% billing paid
Proposed Upgrading/Rehabilitation of Alleys at General Trias St., including Drainage | Hulong Duhat | 591078.31 | 2015-06-01 | 2015-06-30 | 100% | 591078.31 |  | 100% billing paid
Proposed Upgrading/Rehabilitation of Alley at Sulucan St., including Drainage | Hulong Duhat | 2257944.91 | 2015-07-13 | 2015-09-10 | 100% | 2257944.91 |  | 50% billing paid
Proposed Upgrading/Rehabilitation of Donisio St., including Drainage | Maysilo | 1746100.35 | 2015-08-13 | 2015-10-11 | 100% | 1746100.35 |  | 100% billing paid
Proposed Reblocking of Crispin St. | Tinajeros | 2335086.98 | 2015-08-12 | 2015-09-25 | 100% | 2335086.98 |  | 100% billing paid
Proposed Upgrading/Rehabilitation of Alleys at Dulong Hernandez St., including Drainage | Catmon | 1857304.77 | 2015-08-13 | 2015-10-11 | 85% | 1578709.05 |  | 50% billing paid
Proposed Upgrading/Rehabilitation of Concrete Pavement at Tañong Multi-Purpose Area | Tañong | 856092.55 | 2015-08-14 | 2015-10-12 | 100% | 856092.55 |  | 100% billing paid
SOCIAL DEVELOPMENT
Proposed Extension of Catmon Basketball Covered Court | Catmon | 2181793.44 | 2015-06-17 | 2015-08-15 | 100% | 2181793.44 |  | 100% billing paid
ENVIRONMENTAL MANAGEMENT
Proposed Rehabilitation of Drainage Line at Justice Compound beside half court | Catmon | 337686 | 2015-05-04 | 2015-05-27 | 100% | 337686 |  | 100% billing paid
We hereby certify that we have reviewed the contents and hereby attest to
the veracity and correctness of the data or information contained in this
document.
Prepared by : |  | Reviewed by : |  |  |  | Noted by :
CYNTHIA P. RAMOS |  | ENGR. ALAN A. GATPOLINTAN |  |  |  | HON. ANTOLIN A. ORETA III
City Budget Officer |  | City Engineer |  |  |  | City Mayor
Note on A28: USER70:
Note on A29: USER70:
Note on A31: USER70:
Note on A32: USER70: