## 3Q 2017 FUR TF
FDPP Form 6 - Trust Fund Utilization
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES
for the 3rd QUARTER, CY 2017
Province, City or Municipality : Malabon City
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date
Construction of New Pagamutang Bayan ng Malabon | F. Sevilla Blvd. San Agustin ,Malabon City | 142894901 | 2015-07-01 | 2016-04-30 | 98.61% | 140914875.85 |  | P148,125,000.00 is the actual amount received as of date (100% of MOA Total)
Cleaning-Up, Management & Maintenance of Secondary Tributary Waterways of MANATUTI River System | Malabon-Navotas and Tullahan-Tinajaeros River System | 20000000 | 2014-10-01 | September 30,2015 | 50% | 10000000 |  | P10,000,000 is the actual amount received and fully liquidated out of P20M-as per MOA)
Improvement /upgrading of Pagamutang Bayan ng Malabon | Pagamutang Bayan ng Malabon-F. Sevilla Blvd. San Agustin Malab on City | 4904947.39 | March 22, 2016 | June 10, 2016 | 64.13% | 3145748.69 |  | Project partially completed, yet to be paid
Improvement and maintenance of the Malabon City Bureau of Fire Protection Stations | Malabon City Fire Station-# 70 Gov. Pascual Ave. Potrero, Malabon City | 4850522.89 | [5 empty] | in process
Sustainable Livelihood Program | Citiwide | 2005782 | July 2017 | December 2017 |  |  |  | in process
Validation of Community Based Monitoring System(delivery of Information Technology (I.T.) equipment | City Planning Office- 7th floor | 1198000 | September 2017 | December 2017 | 94.37% | 1130500 |  | the unused balance of P67,500.00 will be return to DILG-NCR
Supplemental Feeding Program CY 2017 | Child Development Center and Supervised Neighborhood Play (SNP) areas | 11280000 | [5 empty] | for posting (BAC)
TOTAL |  | 187134153.28 |  |  |  | 155191124.54
Prepared by: |  |  |  |  | Certified correct:
JOSEPHINE C. GOBOY | [5 empty] | HON. ANTOLIN A. ORETA III
OIC - City Accounting Department | [5 empty] | City Mayor