## 4th qtr.
FDP Form 7 - 20% Component of the IRA Utilization
20% COMPONENT OF THE IRA UTILIZATION
FOR THE 4th QUARTER, CY 2014
CITY GOVERNMENT OF MALABON
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date
SOCIAL DEVELOPMENT
Proposed Construction of covered court | located at Catmon Peoples Park, Brgy. Catmon | 5902519.09 | 2014-07-08 | 2014-10-13 | 100% | 5902519.09
Proposed Construction of Multi-Purpose Building | located along C. Arellano St. beside La Purisima Academy Barangay Concepcion | 3002773.6 | 2014-07-08 | 2014-10-13 | 100% | 3002773.6
Proposed Installation of Barbed Wire at Fence of Bahay Sandigan | located at Langaray St., Kaunlaran Village, Brgy. Longos | 259328.85 | 2014-10-27 | 2014-11-28 | 100% | 259328.85
Proposed Construction of Multipurpose Hall | located along Angela St., Brgy. Maysilo | 4967196.89 | 2014-09-22 | 2015-01-22 | 100% | 4967196.89
Proposed Construction of Multipurpose Hall at CMPI | located along Gov. Pascual Ave., Brgy. Baritan | 1607741.32 | 2014-09-19 | 2014-11-14 | 100% | 1607741.32
Proposed Repair/Maintenance of Muzon covered Court | located at Brgy. Muzon | 1295019.55 | 2014-09-22 | 2014-11-03 | 100% | 1295019.55
Proposed Repair of Streetlights at Various Streets and Bridges | located at Various Barangays, City of Malabon | 407221 | 2015-01-05 | 2015-01-10 | 100% | 407221
Proposed Rehabilitation of Lighting at Tugatog Cemetery | located at Brgy. Tugatog, City of Malabon | 432738.5 | 2014-10-31 | 2014-11-03 | 100% | 432738.5
Construction of Covered Court | located at Catmon People's Park -(Variation) | 589633.58 | 2014-10-12 | 2014-10-27 | 100% | 589633.58
Rehabilitation of Covered Court | located at Santiago Syjuco Memorial School - (Variation) | 505757.93 | 2014-10-12 | 2014-10-27 | 100% | 505757.93
ECONOMIC DEVELOPMENT
Proposed upgrading/rehabilitation of Pinagpala, Mapalad and Dakila Sts. | located at Brgy. Tonsuya | 1583531.23 | 2014-07-08 | 2014-07-31 | 100% | 1583531.23
Proposed upgrading/rehabilitation of Damzon St., (portion phase II) | located at Brgy. Dampalit | 2646279.96 | 2014-09-30 | 2014-09-30 | 100% | 2646279.96
Proposed upgrading/rehabilitation of Dulong Bronce / Zinc Sts., (portion) | located at Brgy. Tugatog | 1794554.69 | 2014-09-01 | 2014-11-03 | 100% | 1794554.69
Proposed upgrading/rehabilitation of Javier St., | located at Brgy. Santulan | 2506861.09 | 2014-09-26 | 2014-09-26 | 100% | 2506861.09
Proposed upgrading/rehabilitation of Road (portion) along Hasa - Hasa St., | located at Block 12, Longos | 568935.03 | 2014-08-27 | 2014-10-09 | 100% | 568935.03
Proposed upgrading/rehabilitation of Hiwas Ext. (Teachers Village) | located at Brgy. Longos | 4434432.68 | 2014-09-01 | 2014-10-22 | 100% | 4434432.68
Proposed upgrading/rehabilitation of MOZO-1 | located at Brgy. Maysilo | 397754.53 | 2014-10-27 | 2014-11-20 | 100% | 397754.53
Proposed upgrading/rehabilitation of various alley located at Burgos, ugnatan between Burgos /Villongco and Mabini Sts., | located at Brgy. Concepcion | 846133.42 | 2014-08-26 | 2014-10-11 | 100% | 846133.42
Proposed Re-blocking of Angela St. (portion) | located at Brgy. Maysilo | 1238535.62 | 2014-09-30 | 2014-09-30 | 100% | 1238535.62
Proposed Re-blocking of Pampano St. (portion) | located at Brgy. Longos | 650718.65 | 2014-08-27 | 2014-10-10 | 100% | 650718.65
Proposed Upgrading / Rehabilitation of Santos St., | located at Brgy. San Agustin | 413511.15 | 2014-10-27 | 2014-12-02 | 100% | 413511.15
Proposed Asphalting of M.L. Quezon St. (portion) | located at Brgy. Tugatog | 984440.22 | 2014-08-26 | 2014-09-26 | 100% | 984440.22
Proposed Upgrading / Rehabilitation of Luna II Ext. | located at Brgy. San Agustin | 1005804.97 | 2014-09-01 | 2014-10-13 | 100% | 1005804.97
Proposed Upgrading / Rehabilitation of Burgos St., (portion) | located at Brgy. Concepcion | 1392527.67 | 2014-09-01 | 2014-11-03 | 100% | 1392527.67
Proposed Upgrading / Rehabilitation of Samson & Talabahan Sts. (portion) | located at Brgy. Baritan | 1209726.79 | 2014-09-12 | 2014-11-14 | 100% | 1209726.79
Proposed Upgrading / Rehabilitation of Delos Santos IV & V Sts., | located at Brgy. Tonsuya | 2974828.72 | 2014-09-12 | 2014-11-10 | 100% | 2974828.72
Proposed Upgrading / Rehabilitation of Gabriel St. | located at Brgy. Tonsuya, City of Malabon | 751012.32 | 2014-12-01 | 2015-01-14 | 100% | 751012.32
Proposed Upgrading / Rehabilitation of Rosita St. (completion) | located at Brgy. Santulan, City of Malabon | 1490463.68 | 2014-12-01 | 2015-01-20 | 100% | 1490463.68
Proposed Upgrading / Rehabilitation of Rodriguez St. (portion) | located at Bayan-Bayanan, City of Malabon | 633811.55 | 2014-12-01 | 2015-01-21 | 100% | 633811.55
Proposed Upgrading / Rehabilitation of Bautista St. (completion) | located at Brgy. Panghulo, City of Malabon | 6037959.1 | 2014-12-01 | 2015-03-07 | 100% | 6037959.1
Proposed Upgrading / Rehabilitation of various alleys | located at. Brgy. Hulong Duhat, City of Malabon | 2493419.46 | 2014-12-01 | 2015-01-20 | 100% | 2493419.46
Proposed Upgrading / Rehabilitation of alleys at Block 12 | located at, Brgy. Longos, City of Malabon | 1648553.88 | 2014-12-01 | 2015-02-05 | 100% | 1648553.88
ENVIRONMENTAL MANAGEMENT
Proposed Upgrading / Rehabilitation of Drainage Line | located People's Park Brgy. Catmon | 557333.35 | 2014-08-26 | 2014-09-25 | 100% | 557333.35
Proposed Rehabilitation of Drainage Line at Mesina St., | located at Brgy. Tinajeros | 1001309.67 | 2014-09-01 | 2014-10-14 | 100% | 1001309.67
Proposed Rehabilitation of Drainage Line at A. Reyes St., infront of MRH | located at Brgy. Baritan | 948221.27 | 2014-09-01 | 2014-10-14 | 100% | 948221.27
We hereby certify that we have reviewed the contents and hereby attest to
the veracity and correctness of the data or information contained in this
document.
CYNTHIA P. RAMOS |  |  | HON. ANTOLIN A. ORETA III
City Budget Officer |  |  | City Mayor