## 4Q 2015 TFUR
FDPP Form 6 - Trust Fund Utilization
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES
FOR THE 4th QUARTER, CY 2015
Province, City or Municipality : Malabon City
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date
Construction of New Pagamutang Bayan ng Malabon | F. Sevilla Blvd. San Agustin ,Malabon City | 142894901 | 2015-07-01 | 2016-04-30 | 32.56% | 46531630.8 |  | P74,062,500.00 is the actual amount received as of date (50% of MOA Total) | 74,062,500 (50%, partial amount received)
Rehabilitation of N. Vicencio St. & Portion of F. Nicolas St. Barangay Niugan | Barangay Niugan, Malabon City | 3078652.04 | 2015-04-23 | 2015-07-22 | 50% | 1539362.02 |  | P1,548,884 .00 is the remaining 50% fund which was received last Dec. 28,2015)
Cleaning-Up, Management & Maintenance of Secondary Tributary Waterways of MANATUTI River System | Malabon-Navotas and Tullahan-Tinajaeros River System | 20000000 | 2014-10-01 | September 30,2015 | 49.8% | 9960000 |  | P10,000,000 is the actual amount received, out of P20M-as per MOA)
Hot meal for the implementation of 120 days supplementary feeding program | National Child Development Center and ECCD Home based | 4800000 | October 2015 | March 18,2016 | 37.96% | 1822203.63 |  | on going project
Conversion of DayCare Center to Child Development Center | Barangay Panghulo, Santulan and Tonsuya, Malabon City | 2000000 | 2016-01-04 | 2016-04-02 | 0% | 0 |  | on going project
Bottom Up Budgeting (BUB)-Upgrading/Rehabilitation of the core local road at Barangay Tañong , Malabon City | 1st Street and Main Steet of Barangay Tañong, Malabon City. | 4000000 | October 29,2015 | November 21,215 | 99.39% | 3975538.66 |  | 100% accomplished with cash return of P 24,461.34 to DBM
Bottom Up Budgeting (BUB)-Sustainable Livelihood Program |  | 1900000 | [6 empty] | 4000000
TOTAL |  | 178673553.04 |  |  |  | 63828735.11 |  |  | #REF!
Prepared by: |  |  |  |  | Certified correct:
MARIA LOURDES R. MANLULU | [5 empty] | HON. ANTOLIN A. ORETA III
City Accountant | [5 empty] | City Mayor
Note on G11: PC-71:wages for may 1-june 15,2015