## 4th qtr
FDP Form 7 - 20% Component of the IRA Utilization
20% COMPONENT OF THE IRA UTILIZATION
FOR THE 4th QUARTER, CY 2016
CITY GOVERNMENT OF MALABON
|  | Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[7 empty] | % of Completion | Total Cost Incurred to Date
ECONOMIC DEVELOPMENT
1 | 31 | Proposed Upgrading / Rehabilitation of Kitang Alley along Labahita St. between Blk. 14,15,16 and 17 including drainage | Brgy. Longos | 1382162.66 | 2016-02-22 | 2016-05-21 | 100% | 1382162.66 |  | completed | 1 | 0
2 | 33 | Proposed Upgrading / Rehabilitation of Interior F. Nicolas St. including drainage | Brgy. Niugan | 1345464.14 | 2016-02-22 | 2016-04-21 | 100% | 1345464.14 |  | completed | 2 | 0 | 1278190.933 | 67273.207
3 | 22 | Proposed Upgrading / Rehabilitation of Various Alleys at Celia II St. including drainage (Phase II) | Brgy. Bayan-Bayanan | 2868332.67 | 2016-02-22 | 2016-06-20 | 100% | 2868332.67 |  | completed | 3 | 0 | 2724916.0365 | 143416.6335
4 | 29 | Proposed Upgrading / Rehabilitation of various alleys along Langaray St. between Blk. 14 and 17 including drainage. | Brgy. Longos | 2158030.81 | 2016-02-22 | 2016-05-06 | 100% | 2158030.81 |  | completed | 4 | 0 | 1834326.1885 | 323704.6215
5 | 32 | Proposed Upgrading / Rehabilitation of Alleys at Blk. 15, 16, and Hasa-Hasa St. portion (Road 45) including drainage | Brgy. Longos | 1769776.72 | 2016-02-22 | 2016-05-21 | 100% | 1769776.72 |  | completed | 5 | 0 | 1504310.212 | 265466.508
6 | 30 | Proposed Upgrading / Rehabilitation of Various Alleys along Halaan St. Blk. 2 Phase II including drainage | Brgy. Longos | 1302928.72 | 2016-02-22 | 2016-04-21 | 100% | 1302928.72 |  | completed | 6 | 0 | 1107489.412 | 195439.308
7 | 27 | Proposed Upgrading / Rehabilitation of Various Alleys along Don Basilio Bautista Blvd. including drainage | Brgy. Hulong Duhat | 1428672.29 | 2016-02-22 | 2016-05-21 | 100% | 1428672.29 |  | completed | 7 | 0 | 1428672.29 | 0
8 | 23 | Proposed Upgrading / Rehabilitation of Various Alleys at Jacinto St. including Drainage | Brgy. Concepcion | 2293278.62 | 2016-02-26 | 2016-06-24 | 100% | 2293278.62 |  | completed | 8 | 0 | 1146639.31 | 1146639.31
9 | 26 | Proposed Upgrading / Rehabilitation of Various Alleys at Sulucan St. including drainage (Phase II) | Brgy. Hulong Duhat | 2797630.37 | 2016-02-22 | 2016-06-20 | 100% | 2797630.37 |  | completed | 9 | 0 | 1958341.259 | 839289.111
10 | 36 | Proposed Upgrading / Rehabilitation of Alley at Mendiola St. including drainage | Brgy. Tonsuya | 1130479.21 | 2016-02-22 | 2016-05-06 | 100% | 1130479.21 |  | completed | 10 | 0 | 1130479.21 | 0
11 | 28 | Proposed Upgrading / Rehabilitation of Various Alleys along Dulong Herrera St., including drainage | Brgy. Ibaba | 1300981.66 | 2016-02-22 | 2016-05-21 | 100% | 1300981.66 |  | completed | 11 | 0 | 650490.83 | 650490.83
12 | 48 | Proposed Upgrading / Rehabilitation of Various Alleys at Jacinto St. including drainage (Phase II) | Brgy. Concepcion | 2396322.66 | 2016-03-29 | 2016-06-26 | 100% | 2396322.66 |  | completed | 12 | 0
13 | 25 | Proposed Upgrading / Rehabilitation of Alley along A. Gervacio St. including drainage | Brgy. Hulong Duhat | 383642.21 | 2016-03-16 | 2016-04-29 | 100% | 383642.21 |  | completed | 13 | 0
14 | 41 | Proposed Upgrading / Rehabilitation of Various Alleys along Pampano St. at Blk. 49 including drainage | Brgy. Longos | 3536653.78 | 2016-03-29 | 2016-07-26 | 100% | 3536653.78 |  | completed | 14 | 0
15 | 42 | Proposed Upgrading / Rehabilitation of Various Alleys along Hito St. Blk.3 including drainage | Brgy. Longos | 1170818.47 | 2016-03-29 | 2016-05-27 | 100% | 1170818.47 |  | completed | 15 | 0
16 | 43 | Proposed Upgrading / Rehabilitation of Hito St. (Portion) including Drainage | Brgy. Longos | 2318301.28 | 2016-03-29 | 2016-05-27 | 100% | 2318301.28 |  | completed | 16 | 0
17 | 24 | Proposed Upgrading / Rehabilitation of Alley at Escanilla St. (Portion) including drainage | Brgy. Concepcion | 291566.37 | 2016-03-16 | 2016-04-29 | 100% | 291566.37 |  | completed | 17 | 0
18 | 21 | Proposed Upgrading / Rehabilitation of Various Alleys at Javier II (Phase II) including drainage | Brgy. Baritan | 2448854.58 | 2016-02-22 | 2016-05-21 | 100% | 2448854.58 |  | completed | 18 | 0
19 | 49 | Proposed Upgrading / Rehabilitation of Alley along Hiwas St. Blk 10 Phase 2 | Brgy. Longos | 243122.96 | 2016-05-29 | 2016-04-27 | 100% | 243122.96 |  | completed | 19 | 0
20 | 45 | Proposed Upgrading / Rehabilitation of Cristina St. (Portion) including Drainage | Brgy. Panghulo | 719714.1 | 2016-03-29 | 2016-05-12 | 100% | 719714.1 |  | completed | 20 | 0
21 | 46 | Proposed Rehabilitation of Duhat Road (Portion) including Drainage | Brgy. Potrero | 2717037.77 | 2016-03-29 | 2016-05-27 | 100% | 2717037.77 |  | completed | 21 | 0
22 | 35 | Proposed Upgrading / Rehabilitation of Various Alleys along Custodio St. including drainage (Phase II) | Brgy. Santulan | 2142344.3 | 2016-02-22 | 2016-05-21 | 100% | 2142344.3 |  | completed | 22 | 0
23 | 47 | Proposed Reblocking of Custodio St. and Mabolo St. | Brgy. Santulan | 3715108.67 | 2016-03-29 | 2016-06-26 | 100% | 3715108.67 |  | completed | 23 | 0
24 | 34 | Proposed Upgrading / Rehabilitation of Various Alleys along J.M. Templora St. including drainage | Brgy. Santulan | 629036.5 | 2016-03-04 | 2016-05-02 | 100% | 629036.5 |  | completed | 24 | 0
25 | 39 | Proposed Upgrading / Rehabilitation of Aluminio St. (Portion) including drainage | Brgy. Tugatog | 3335428.85 | 2016-03-29 | 2016-06-26 | 100% | 3335428.85 |  | completed | 25 | 0
26 | 38 | Proposed Upgrading / Rehabilitation of Estanio St. (Portion) including drainage | Brgy. Tugatog | 2108660.17 | 2016-03-29 | 2016-06-11 | 100% | 2108660.17 |  | completed | 26 | 0
27 | 37 | Proposed Upgrading / Rehabilitation of Plata St. (Portion) including drainage | Brgy. Tugatog | 901498.18 | 2016-03-29 | 2016-05-12 | 100% | 901498.18 |  | completed | 27 | 0
28 | 40 | Proposed Rehabilitation of Sanchez St. (Portion) including drainage | Brgy. Tinajeros | 4990609.13 | 2016-03-29 | 2016-06-26 | 100% | 4990609.13 |  | completed | 28 | 0
29 | 53 | Proposed Upgrading / Rehabilitation of Various Alleys along Maya-Maya St. at Blk. 50 including drainage (Phase II) | Brgy. Longos | 195935.05 | 2016-05-10 | 2016-06-08 | 100% | 195935.05 |  | completed | 29 | 0
30 | 50 | Proposed Upgrading / Rehabilitation of Alupihang Dagat St. (Portion) including drainage | Brgy. Longos | 2225434.41 | 2016-05-17 | 2016-07-15 | 100% | 2225434.41 |  | completed | 30 | 0
31 | 44 | Proposed Upgrading / Rehabilitation of Various Alleys along Hiwas St. at Blk. 8 and 9 including drainage | Brgy. Longos | 1749877.16 | 2016-05-17 | 2016-07-30 | 100% | 1749877.16 |  | completed | 31 | 0
32 | 51 | Proposed Upgrading / Rehabilitation of Alleys along Liwayway St. including drainage | Brgy. Bayan-Bayanan | 1451699.63 | 2016-08-22 | 2016-10-20 | 100% | 1451699.63 |  | completed | 32 | 0
33 | 52 | Proposed Rehabilitation of Various Alleys at Matadero St. including drainage | Brgy. San Agustin | 2326462.36 | 2016-08-22 | 2016-11-19 | 100% | 2326462.36 |  | completed | 33 | 0
34 | 54 | Proposed Upgrading / Rehabilitation of Celia II St. and Alley at Celia I St. including drainage | Brgy. Bayan-Bayanan | 1982576.36 | 2016-08-22 | 2016-11-19 | 100% | 1982576.36 |  | completed | 34 | 0 | 1883447.542 | 99128.818
35 | 55 | Proposed Upgrading / Rehabilitation of Ma. Leni St. (Portion) including drainage | Brgy. Hulong Duhat | 3591350.55 | 2016-08-22 | 2016-11-19 | 100% | 3591350.55 |  | completed | 35 | 0 | 2513945.385 | 1077405.165
36 | 56 | Proposed Upgrading / Rehabilitation of Patrick St. including drainage | Brgy. Hulong Duhat | 743546.94 | 2016-08-22 | 2016-10-20 | 100% | 743546.94 |  | completed | 36 | 0 | 520482.858 | 223064.082
37 | 57 | Proposed Upgrading / Rehabilitation of Cherry Gail St. (Portion) including drainage | Brgy. Hulong Duhat | 3269078.23 | 2016-08-22 | 2016-11-19 | 100% | 3269078.23 |  | completed | 37 | 0 | 2288354.761 | 980723.469
38 | 58 | Proposed Upgrading / Rehabilitation of Various Alleys along Maya-Maya St., Blk. 43 & Blk. 45 including drainage | Brgy. Longos | 1490554 | 2016-09-12 | 2016-11-10 | 100% | 1490554 |  | completed | 38 | 0
|  | Proposed Upgrading / Rehabilitation of Champaca St. including drainage | Brgy. Longos | 668276.87 | 2016-10-05 | 2016-12-03 | 100% | 668276.87 |  | completed Nov. 9, 2016
|  | Proposed Upgrading / Rehabilitation of Gutierrez St. (Completion) including drainage | Brgy. Panghulo | 4340137 | 2016-11-21 | 2017-02-18 | 100% | 4340137 |  | completed Dec. 21, 2016
|  | Proposed Upgrading / Rehabilitation of Sampaguita St. including drainage | Brgy. Longos | 1547529 | 2016-11-21 | 2017-02-18 | 70% | 1083270.3 |  | on - going
|  | Proposed Upgrading / Rehabilitation of Jasmin St. and Kampupot St.including drainage | Brgy. Longos | 1237031 | 2016-11-21 | 2017-02-03 | 70% | 865921.7 |  | on - going
|  | Proposed Reblocking of Yanga St. (Portion) including drainage (Phase II) | Brgy. Maysilo | 5194906.18 | 2016-11-23 | 2017-02-20 | 100% | 5194906.18 |  | completed Dec. 14, 2016
|  | Proposed Rehabilitation and Repair of Guava Road (Portion) Phase II | Brgy. Potrero | 1790256.46 | 2016-11-23 | 2017-01-06 | 100% | 1790256.46 |  | completed Dec. 6, 2016
|  | Proposed Upgrading / Rehabilitation of Various Alleys at Javier II (Phase III) including drainage | Brgy. Baritan | 3390400.19 | 2016-11-25 | 2017-03-24 | 100% | 3390400.19 |  | completed Dec. 19, 2016
0
|  |  |  | 91021509.24 |  |  |  | 90186141.24 |  |  |  | 835368
|  | SOCIAL DEVELOPMENT | [9 empty] | 0
1 | 1 | Proposed Installation of Five (5) Sets of Streetlights along Paez Street | Brgy. Concepcion | 508994.27 | 2016-03-29 | 2016-04-27 | 100% | 508994.27 |  | completed | 39 | 0
2 | 14 | Proposed Construction of Potrero Multi-Purpose Hall located at Camachile St. | Brgy. Potrero | 3744743.1 | 2016-02-22 | 2016-05-21 | 100% | 3744743.1 |  | completed | 40 | 0
3 | 2 | Proposed Rehabilitation of Streetlights at Various Streets in Various Brgy. City of Malabon | Various Brgy. | 1768581 | 2016-03-22 | 2016-05-30 | 100% | 1768581 |  | completed | 41 | 0
4 | 11 | Proposed Rehabilitation of Manpower Development Centre (Laboratory) at CMPI located at Gov. Pascual Ave. corner A. Reyes St. | Brgy. Baritan | 175516.97 | 2016-05-10 | 2016-05-24 | 100% | 175516.97 |  | completed | 42 | 0
5 | 5 | Proposed Installation of Ten (10) Sets of Streetlights along Macopa Road | Brgy. Potrero | 1126977.36 | 2016-07-06 | 2016-08-04 | 100% | 1126977.36 |  | completed | 43 | 0
6 | 4 | Proposed Installation of Five (5) Sets of Streetlights along Santol Street | Brgy. Potrero | 638051.97 | 2016-07-06 | 2016-08-04 | 100% | 638051.97 |  | completed | 44 | 0
7 | 3 | Proposed Installation of Twelve (12) Sets of Streetlights along Duhat Road | Brgy. Potrero | 1402360.98 | 2016-07-06 | 2016-08-19 | 100% | 1402360.98 |  | completed | 45 | 0
8 | 7 | Proposed Installation of Electric Service Entrance for Pampano Multi-Purpose Hall, Pampano St. | Brgy. Longos | 17112 | 2016-09-16 | 2016-09-20 | 100% | 17112 |  | completed | 46 | 0
9 | 6 | Proposed Installation of Streetlights Lamp Post and Electric Service Entrance at Talilong Park. | Brgy. Tinajeros | 21588 | 2016-09-16 | 2016-09-21 | 100% | 21588 |  | completed Supplies Materials only | 47 | 0
10 | 16 | Proposed Upgrading / Rehabilitation of Bayan-Bayanan Covered Court at Celia II St. | Brgy. Bayan-Bayanan | 3038679.2 | 2016-08-22 | 2016-11-19 | 100% | 3038679.2 |  | completed | 48 | 0 | 2886745.24 | 151933.96
11 | 8 | Proposed Installation of Six (6) Sets of Streetlights at Sisa Extension | Brgy. Tinajeros | 486308.78 | 2016-08-11 | 2016-09-09 | 100% | 486308.78 |  | completed | 49 | 0
12 | 12 | Proposed Rehabilitation of Manpower Development Centre (Workshop Area) at CMPI located at Gov. Pascual Ave. corner A. Reyes St. | Brgy. Baritan | 410127.01 | 2016-08-11 | 2016-09-24 | 100% | 410127.01 |  | completed | 50 | 0
13 | 10 | Proposed Installation of Thirteen (13) Sets of Streetlights at Panghulo Road | Brgy. Panghulo | 1423066.95 | 2016-09-02 | 2016-10-16 | 100% | 1423066.95 |  | completed | 51 | 0
14 | 9 | Proposed Installation of Twenty - Five (25) Sets of Streetlights from Catmon Bridge to Umboy Creek | Brgy. Catmon | 2720797.86 | 2016-09-02 | 2016-11-30 | 100% | 2720797.86 |  | completed | 52 | 0
15 | 17 | Proposed Construction of Concepcion Multi-Purpose Hall at Jacinto St. | Brgy. Concepcion | 1345300 | 2016-09-12 | 2016-11-25 | 100% | 1345300 |  | completed | 53 | 0
|  | Proposed Adjustment of PWD Ramp at Old PBM | Brgy. Longos | 40245 | 2016-12-01 | 2016-12-09 | 100% | 40245 |  | completed Dec. 9, 2016
|  | Proposed Rehabilitation / Repair of Santulan Multi-Purpose Building (Señior Citizens Hall) at E. Martin St. | Brgy. Santulan | 1361056.67 | 2016-11-23 | 2017-03-02 | 100% | 1361056.67 |  | completed Dec. 15, 2016
|  | Proposed Rehabilitation of Manpower Development Center (Workshop Area) at Vicencio Bldg. at CMPI located at Gov. Pascual Ave., Corner A. Reyes St. | Brgy. Baritan | 345300 | 2016-12-12 | 2016-12-31 | 100% | 345300 |  | completed
|  | Proposed Construction of Waiting Shed along Crispin St. located at Tinajeros Elementary School | Brgy. Tinajeros | 239943.11 | 2016-12-08 | 2017-01-06 | 100% | 239943.11 |  | completed Dec. 15, 2016
|  | Proposed Construction and Rehabilitation of Waiting Shed along San Antonio St. located at San Vicente Village | Brgy. Maysilo | 265717.36 | 2016-12-08 | 2017-01-06 | 100% | 265717.36 |  | completed Dec. 15, 2016
1 | 2 | Proposed Rehabilitation of Streetlights at Various Streets in Various Brgy. City of Malabon | Various Brgy. | 461474 | 2016-12-27 | 2016-12-31 | 100% | 461474 |  | completed Supplies Materials only | 1 | 0
|  | Proposed Installation of Twenty - One (21) Sets of LED Streetlights along E. Martin Street | Brgy. Santulan | 2130000 | 2016-12-21 | 2017-02-03 | 50% | 1065000 |  | completed
|  | Proposed Installation of Thirteen (13) Sets of LED Streetlights along M. Santos Street | Brgy. Santulan | 1365000 | 2016-12-21 | 2017-01-19 | 50% | 682500 |  | completed
|  |  |  | 25036941.59 |  |  |  | 23289441.59
|  | ENVIRONMENTAL MANAGEMENT | [8 empty] | 1 | 0 | 634331.32
1 | 70 | Proposed Upgrading / Rehabilitation of Drainage Canal along Asogue St. leading to Tugatog Pumping Station | Brgy. Tugatog | 634331.32 | 2016-03-04 | 2016-04-17 | 100% | 634331.32 |  | completed | 2 | 0 | 1480213.2115
2 | 71 | Proposed Rehabilitation of Drainage Canal at Karen St. | Brgy. Hulong Duhat | 1558119.17 | 2016-02-22 | 2016-04-06 | 100% | 1558119.17 |  | completed | 3 | 0
3 | 67 | Proposed Installation of Garbage Trash Trap at Spine Canal along Lapu-Lapu Avenue | Brgy. Longos | 286090.58 | 2016-03-16 | 2016-04-29 | 100% | 286090.58 |  | completed | 4 | 0 | 512852.21
4 | 74 | Proposed Linear Park Development along the Easement of Tullahan River (Portion) | Brgy. Potrero | 512852.21 | 2016-07-06 | 2016-08-19 | 100% | 512852.21 |  | completed | 5 | 0
5 | 73 | Proposed Construction of Drainage Line (Portion) at Justice Compound, Sanciangco St. | Brgy. Catmon | 1965819.5 | 2016-08-22 | 2016-11-19 | 100% | 1965819.5 |  | completed | 6 | 0 | 1301945.55
6 | 72 | Proposed Rehabilitation / Construction of Drainage Canal along Maya-Maya St. | Brgy. Longos | 4519469 | 2016-09-12 | 2016-12-10 | 40% | 1807787.6 |  | completed | 7 | 2711681.4 | 1301945.55
|  | Proposed Vertical Wall Greening along C-4 Road (Portion) Sixteen (16) Bays | Brgy. Tañong | 1370469 | 2016-11-21 | 2017-01-19 | 85% | 1164898.65 |  | on - going
|  | Proposed Rehabilitation of Javier II - Pumping Station & Flood Gate, Javier II St. | Brgy. Baritan | 1205413.78 | 2016-11-21 | 2017-01-04 | 95% | 1145143.091 |  | on - going
|  | Proposed Rehabilitation of Bernadette Flood Gate & Drainage Line, Gov. Andres St. corner Bernadette St., Gabriel Subdivision | Brgy. Hulong Duhat | 420151.68 | 2016-12-08 | 2017-01-16 | 100% | 420151.68 |  | completed Dec. 14, 2016
|  |  |  | 12472716.24 |  |  |  | 9495193.801
|  |  |  | 128531167.07 |  |  |  | 122970776.631
|  | Prepared by : |  | Reviewed by: |  |  |  | Noted by :
|  | CYNTHIA P. RAMOS |  | ENGR. RUTH B. SENAIDA |  |  |  | HON. ANTOLIN A. ORETA III
|  | City Budget Officer |  | OIC - City Engineering Dept. |  |  |  | City Mayor