## 4Q 2016 TF Utilization
FDPP Form 6 - Trust Fund Utilization
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES
FOR THE 4th QUARTER, CY 2016
Province, City or Municipality : Malabon City
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date
Construction of New Pagamutang Bayan ng Malabon | F. Sevilla Blvd. San Agustin ,Malabon City | 142894901 | 2015-07-01 | 2016-04-30 | 96.83% | 138370426.73 |  | P148,125,000.00 is the actual amount received as of date (100% of MOA Total) | 74,062,500 (50%, partial amount received) | 148117987.58
Cleaning-Up, Management & Maintenance of Secondary Tributary Waterways of MANATUTI River System | Malabon-Navotas and Tullahan-Tinajaeros River System | 20000000 | 2014-10-01 | September 30,2015 | 50% | 10000000 |  | P10,000,000 is the actual amount received and fully liquidated out of P20M-as per MOA)
Bottom Up Budgeting (BUB)-Sustainable Livelihood Program | Various barangay in Malabon City | 1900000 | March 16,2016 | 2016-06-02 | 100% | 1732780 |  | Unused amount of P167,220.00 was returned to DSWD-NCR (check # 249550 dated 10/3/16
Rehabilitation and Drainage Improvement of Gutierrez St. (portion) located at Barangay Panghulo, Malabon City | Gutierrez St. Panghulo Malabon City | 2943541 | August 22,2016 | November 4,2016 | 99.34% | 2924093.089 |  | project completed -unused amount of P 16,447.92 will be return to DPWH
Hotmeal intended for the implementation of 120 days Supplemental Feeding Program for CY 2016 for the benefit of 53 day care centers | National Child Development Center and ECCD Home based | 5280000 | September 26,2016 | March 15,2017 | 46.89% | 2475710 |  | On going
Implementation of Fishery Projects under Bottom up Budgeting . | Barangay Concepcion,Flores,Hulong Duhat, Ibaba, Tañong, Bayan-Bayanan, Panghulo, Dampalit | 526229 | November 2016 | December 2016 | 99.68% | 524557 |  | project completed -unused amount of P 1,672.00 will be return to BFAR
Improvement /upgrading of Pagamutang Bayan ng Malabon | Pagamutang Bayan ng Malabon-F. Sevilla Blvd. San Agustin Malab on City | 4904947.39 | March 22, 2016 | June 10, 2016 | 64.13% | 3145748.69 |  | Project partially completed, yet to be paid
TOTAL |  | 178449618.39 |  |  |  | 159173315.509
Prepared by: |  |  |  |  | Certified correct:
JOSEPHINE C. GOBOY | [5 empty] | HON. ANTOLIN A. ORETA III
OIC - City Accounting Department | [5 empty] | City Mayor