## TF FUR 4Q2017
FDPP Form 6 - Trust Fund Utilization
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES
for the 4th QUARTER, CY 2017
Province, City or Municipality : Malabon City
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date
Improvement and maintenance of the Malabon City Bureau of Fire Protection Stations | Malabon City Fire Station-# 70 Gov. Pascual Ave. Potrero, Malabon City | 4850522.89 | [5 empty] | in process
Sustainable Livelihood Program | Citiwide | 1399382 | July 2017 | December 2017 | 100% | 1399382 |  | Project completed
Intensified Reinforcement of Filipino Value | Penthouse, Malabon City | 606400 | December 11,2017 | December 13,2017 |  |  |  | Project completed, yet to be paid
Validation of Community Based Monitoring System(delivery of Information Technology (I.T.) equipment | City Planning Office- 7th floor | 1198000 | September 2017 | December 2017 | 94.37% | 1130500 |  | the unused balance of P67,500.00 was returned to DILG-NCR under DILG O.R. # 7939065 dated 11/6/17
Supplemental Feeding Program CY 2017 | Child Development Center and Supervised Neighborhood Play (SNP) areas | 11280000 | [5 empty] | for posting (BAC)
Equipping of Barangay Health Center with Lying-in | Barangay Health Center withy lying - in | 1000000 | [5 empty] | in process
Integrated Community Food Production | Barangay Catmon, Malabon City | 510000 | November 20,2017 | November 20,2018 |  |  |  | on going
Upgrading Production Capability of Malabon City Jail Bakery | Malabon City Jail | 334400
Construction of the Community Based Treatment and Rehabilitation Facility |  | 5000000 | [5 empty] | The said amount was recently received this December 22,2017 under LGU O.R. # 3964782 dated 12/22/17
2017 SGLG Awardee |  | 2400000 | [5 empty] | The said amount was recently received this December 29,2017 under LGU O.R. # 3964788 dated 12/29/17
TOTAL |  | 28578704.89 |  |  |  | 2529882
Prepared by: |  |  |  |  | Certified correct:
JOSEPHINE C. GOBOY | [5 empty] | HON. ANTOLIN A. ORETA III
OIC - City Accounting Department | [5 empty] | City Mayor