## TF UR SEPT2018
FDPP Form 6 - Trust Fund Utilization
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES
for the 3rd QUARTER, CY 2018
Province, City or Municipality : Malabon City
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date
Construction of New Pagamutang Bayan ng Malabon | F. Sevilla Blvd. San Agustin ,Malabon City | 142894901 | 2015-07-01 | 2016-04-30 | 98.61% | 140914875.85 |  | P148,125,000.00 is the actual amount received as of date (100% of MOA Total)
Cleaning-Up, Management & Maintenance of Secondary Tributary Waterways of MANATUTI River System | Malabon-Navotas and Tullahan-Tinajaeros River System | 20000000 | 2014-10-01 | September 30,2015 | 50% | 10000000 |  | P10,000,000 is the actual amount received and fully liquidated out of P20M-as per MOA)
Improvement and maintenance of the Malabon City Bureau of Fire Protection Stations | Malabon City Fire Station-# 70 Gov. Pascual Ave. Potrero, Malabon City | 4850522.89 |  |  | 69.85% | 3388030 |  | on going
Supplemental Feeding Program CY 2017 | Child Development Center and Supervised Neighborhood Play (SNP) areas | 11280000 | January 3, 2018 | May 5, 2018 | 99.73% | 11249682.6 |  | project completed: the unutilized amount of P 30,317.40 was returned under check no.249781 dated 7/4/18 acknowledged by O.R. # 6905689 dtd. 7/9/18
Equipping of Barangay Health Center with Lying-in | Barangay Health Center withy lying - in | 1000000 | [5 empty] | procurement in process
Integrated Community Food Production | Barangay Catmon, Malabon City | 510000 | November 20,2017 | November 20,2018 | 76.18% | 388535 |  | on going
Upgrading Production Capability of Malabon City Jail Bakery | Malabon City Jail | 334400 | [5 empty] | not yet implemented
Construction of the Community Based Treatment and Rehabilitation Facility | Justice Compound, Brgy. Catmon, Malabon City | 5000000 | [5 empty] | Bidded, waiting for Notice to Proceed (NTP)
Enhancement of Malabon City Birthing Clinic | Pagamutang Bayan ng Malabon | 2400000 | March 13, 2018 |  | 90% | 0 |  | Partial delivery of items for the project total amount of P 2,396,600.00
Supplemental Feeding Program CY 2018 | Child Development Center and Supervised Neighborhood Play (SNP) areas | 11700000 | [5 empty] | for bidding
Local Health Systems Development AssistanceProgram | Malabon City | 1649380 | August 2018 | March 2019 |  |  |  | procurement in process
TOTAL |  | 201619203.89 |  |  |  | 165941123.45
Prepared by: |  |  |  |  | Certified correct:
ATTY. ROCHELLE ANDREA B. RIZADA | [5 empty] | HON. ANTOLIN A. ORETA III
OIC - City Accounting Department | [5 empty] | City Mayor