## 4Q2018 TFU
FDPP Form 6 - Trust Fund Utilization
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES
for the 4th QUARTER, CY 2018
Province, City or Municipality : Malabon City
| Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
NGAS | [5 empty] | % of Completion | Total Cost Incurred to Date
| Construction of New Pagamutang Bayan ng Malabon | F. Sevilla Blvd. San Agustin ,Malabon City | 142894901 | 2015-07-01 | 2016-04-30 | 98.61% | 140914875.85 |  | P148,125,000.00 is the actual amount received as of date (100% of MOA Total)
| Cleaning-Up, Management & Maintenance of Secondary Tributary Waterways of MANATUTI River System | Malabon-Navotas and Tullahan-Tinajaeros River System | 20000000 | 2014-10-01 | September 30,2015 | 50% | 10000000 |  | P10,000,000 is the actual amount received and fully liquidated out of P20M-as per MOA)
| Improvement and maintenance of the Malabon City Bureau of Fire Protection Stations | Malabon City Fire Station-# 70 Gov. Pascual Ave. Potrero, Malabon City | 4850522.89 |  |  | 69.85% | 3388030 |  | on going project
BUB-BOT | Equipping of Barangay Health Center with Lying-in | Barangay Health Center withy lying - in | 1000000 |  | March 2018 | 99.64% | 996396.5 |  | Project completed(purchased Medical Supplies and Equipment).Unused amount of P3,603.50 will be return to the Bureau of the Treasury
| Integrated Community Food Production | Barangay Catmon, Malabon City | 510000 | November 20,2017 | November 20,2018 | 76.18% | 388535 |  | Unused balance of P121,465 will be return to the Bureau of the Treasury
| Upgrading Production Capability of Malabon City Jail Bakery | Malabon City Jail | 334400 | [5 empty] | in process
| Construction of the Community Based Treatment and Rehabilitation Facility | Justice Compound, Brgy. Catmon, Malabon City | 5000000 | October 26,2018 | February 22,2019 | 49.95% | 2497428.76 |  | 1st and Partial ( 50% ) Payment for the Construction of Malabon Drug Treatment Outpatient Clinic
| Enhancement of Malabon City Birthing Clinic | Pagamutang Bayan ng Malabon | 2400000 | March 13, 2018 |  |  |  |  | Partial delivery of items for the project has a total amount of P2,352,120.00
DSWD-NCR | Supplemental Feeding Program CY 2018 | Child Development Center and Supervised Neighborhood Play (SNP) areas | 11700000 | December 3,2018 | April 2019 | 13.62% | 1593333 |  | on going project
| Local Health Systems Development AssistanceProgram | Malabon City | 1649380 | August 2018 | March 2019 |  |  |  | procurement in process
DOH-NCRO | Medical Assistance to Indigents and poor (MAIP) | Ospital ng Malabon | 150000 | December 10,2018 | December 28,2018 | 100% | 150000 |  | Project completed
NNC-NCR | NNC financial assistance for the services of 24 new Barangay Nutrition Scholar | various barangay in Malabon City | 28300 |  |  | 100% | 28300 |  | Project completed for the Travelling allowance of 24 BNSs for 12 months
Bureau of the Treasury-NCR | Construction of Pinagsabugan Linear Park in Barangay Longos(Local Government Support Fund -Assistance to Cities) | Barangay Longos | 12094305 | [5 empty] | procurement in process
DILG-NCR | Performance Challenge Fund for being one of the 2018 SGLG Awardees |  | 5100000 | [5 empty] | not yet implemented
| TOTAL |  | 190339203.89 |  |  |  | 159778599.11
| Prepared by: |  |  |  |  | Certified correct:
| ATTY. ROCHELLE ANDREA B. RIZADA | [5 empty] | HON. ANTOLIN A. ORETA III
| OIC - City Accounting Department | [5 empty] | City Mayor