## 2Q 2019 TFUR
FDPP Form 6 - Trust Fund Utilization
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES
for the 2nd QUARTER, CY 2019
Province, City or Municipality : Malabon City
| Program or Project |  | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
NGAS |  | Source Agency |  |  |  |  | % of Completion | Total Cost Incurred to Date
DPWH | Construction of New Pagamutang Bayan ng Malabon | DPWH | F. Sevilla Blvd. San Agustin ,Malabon City | 142894901 | 2015-07-01 | 2016-04-30 | 98.61% | 140914875.85 |  | P148,125,000.00 is the actual amount received as of date (100% of MOA Total)
BUREAU OF FIRE | Improvement and maintenance of the Malabon City Bureau of Fire Protection Stations | Bu of Fire | Malabon City Fire Station-# 70 Gov. Pascual Ave. Potrero, Malabon City | 4850522.89 |  |  | 97.02% | 4706030 |  | Remaining fund balance is P144,492.89
DOST | Upgrading Production Capability of Malabon City Jail Bakery |  | Malabon City Jail | 334400 |  |  | 99.99% | 334370.54 |  | Project completed : has purchased supplies and equipment for the upgrading of Production Capability of Malabon City Jail Bakery: the unused amount of P 29.46 will be returned to DOST.
DANGEROUS DRUG BOARD | Construction of the Community Based Treatment and Rehabilitation Facility |  | Justice Compound, Brgy. Catmon, Malabon City | 5000000 | October 26,2018 | February 22,2019 | 99.89% | 4994632 |  | Project completed , the remaining fund balance of P 5,368.00 will be return to DRB
DSWD-NCR | Supplemental Feeding Program CY 2018 |  | Child Development Center and Supervised Neighborhood Play (SNP) areas | 11700000 | December 3,2018 | April 2019 | 94.3% | 11033214 |  | Project Completed .The unused amount of P666,786.00 was returned to DSWDD under O.R. # 4744177 dated 6/4/19.
DOH-NCR | Local Health Systems Development AssistanceProgram |  | Malabon City | 1649380 | August 2018 | March 2019 | 72.95% | 1203154 |  | on going project
Bureau of the Treasury-NCR | Construction of Pinagsabugan Linear Park in Barangay Longos(Local Government Support Fund -Assistance to Cities) |  | Barangay Longos | 12094305 |  |  | 14.98% | 1811766.6 |  | on going project
DILG-NCR | Performance Challenge Fund -To procure medical equipment and machineries for the City of Malabon Health Care Facilities | DILG | Malabon Health Care Facilities | 5100000 | [5 empty] | Included in the 2019 AIP for the procurement of medical equipment and machineries
DOH-NCR | Fund from DOH for the implementation of Medical Assistance Program for the indigent and poor patients in OSMAL | DOH-MAIP | Ospital ng Malabon | 1000000 |  |  | 18.13% | 181266.65 |  | on going project
DOH-NCR | Transfer for CIPH 2015 |  |  | 805800 | [5 empty] | Date received: June 13,2019 . For project proposal
| TOTAL |  |  | 185429308.89 |  |  |  | 165179309.64
| Prepared by: | [5 empty] | Certified correct:
| ATTY. ROCHELLE ANDREA B. RIZADA | [6 empty] | HON. ANTOLIN A. ORETA III
| OIC - City Accounting Department | [6 empty] | City Mayor