## 4th qtr
FDP Form 7 - 20% Component of the IRA Utilization
FDP Form 7 - 20% Development Fund Utilization
UTILIZATION OF THE 20% COMPONENT OF IRA FOR DEVELOPMENT PROJECTS
4th QUARTER, CY 2019
Province, City or Municipality : CITY GOVERNMENT OF MALABON
| Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[6 empty] | % of Completion | Total Cost Incurred to Date
| SOCIAL DEVELOPMENT | [8 empty] | 128711679
1 | Proposed Installation of Thirty (30) Sets of LED Streetlights along Basilio Street | Brgy. Acacia | 2964051 | 2019-03-11 | 2019-04-24 | 100% | 2959522 |  | completed
2 | Proposed Installation of Twenty - Five (25) Sets of LED Streetlights along Salmon Street | Brgy. Longos | 2471077 | 2019-03-11 | 2019-04-24 | 100% | 2466966 |  | completed
2 | Proposed Installation of Twenty - One (21) Sets of LED Streetlights along Kagitingan Street (Phase I) | Brgy. Muzon | 2074773 | 2019-03-11 | 2019-04-24 | 100% | 2070251 |  | completed
1 | Proposed Installation of Twenty - One (21) Sets of LED Streetlights at M. H. del Pilar Street, Dionision Street and Yanga Street | Brgy. Maysilo | 2074773 | 2019-03-11 | 2019-04-24 | 100% | 2070098 |  | completed
3 | Proposed Installation of Fifty - Four (54) Sets of LED Streetlights at Various Alleys | Brgy. Bayan-Bayanan | 1958338 | 2019-03-11 | 2019-04-24 | 100% | 1953829 |  | completed
1 | Proposed Installation of Seventeen (17) Sets of LED Streetlights along J. Cancio Street | Brgy. Dampalit | 1679870 | 2019-03-11 | 2019-04-09 | 100% | 1675993 |  | completed
1 | Proposed Installation of Thirty - Nine (39) Sets of LED Streetlights at Remegio Street (Portion) & M.H. Del Pilar Street (Portion) and Various Alleys | Brgy. Maysilo | 1413519 | 2019-03-11 | 2019-04-24 | 100% | 1409072 |  | completed
1 | Proposed Installation of Fourteen (14) Sets of LED Streetlights along N. Vicencio Street | Brgy. Niugan | 1385144 | 2019-03-11 | 2019-04-09 | 100% | 1381647 |  | completed
1 | Proposed Installation of Thirteen (13) Sets of LED Streetlights along Guava Street (Phase II) | Brgy. Potrero | 1284454 | 2019-03-11 | 2019-04-09 | 100% | 1280020 |  | completed
2 | Proposed Installation of Twelve (12) Sets of LED Streetlights along Pampano Street | Brgy. Longos | 1187374 | 2019-03-11 | 2019-04-09 | 100% | 1184221 |  | completed
3 | Proposed Installation of Twelve (12) Sets of LED Streetlights along Hito Street | Brgy. Longos | 1187374 | 2019-03-11 | 2019-04-09 | 100% | 1184221 |  | completed
4 | Proposed Installation of Twelve (12) Sets of LED Streetlights along S. Pascual Street | Brgy. San Agustin | 1187374 | 2019-03-11 | 2019-04-09 | 100% | 1182940 |  | completed
1 | Proposed Installation of Twelve (12) Sets of LED Streetlights along Inocencia Street | Brgy. Tugatog | 1187374 | 2019-03-11 | 2019-04-09 | 100% | 1182491 |  | completed
5 | Proposed Installation of Twelve (12) Sets of LED Streetlights along Liwayway Street | Brgy. Bayan-Bayanan | 1187374 | 2019-03-11 | 2019-04-09 | 100% | 1182491 |  | completed
6 | Proposed Installation of Twelve (12) Sets of LED Streetlights along Katipunan Street | Brgy. Bayan-Bayanan | 1187374 | 2019-03-11 | 2019-04-09 | 100% | 1182491 |  | completed
1 | Proposed Installation of Thirty (30) Sets of LED Streetlights at Padua Street, Ceramic Street and Various Alleys | Brgy. Santulan | 1087495 | 2019-03-11 | 2019-04-24 | 100% | 1083285 |  | completed
4 | Proposed Installation of Eleven (11) Sets of LED Streetlights along Estanio Street | Brgy. Tugatog | 1086682 | 2019-03-11 | 2019-04-09 | 100% | 1081924 |  | completed
2 | Proposed Installation of Eleven (11) Sets of LED Streetlights along Mangustan Street | Brgy. Potrero | 1086682 | 2019-03-11 | 2019-04-09 | 100% | 1081885 |  | completed
3 | Proposed Installation of Eleven (11) Sets of LED Streetlights at Delos Santos One (1) and Delos Santos Two (2) Streets | Brgy. Tonsuya | 1086682 | 2019-03-11 | 2019-04-09 | 100% | 1081885 |  | completed
1 | Proposed Installation of Ten (10) Sets of LED Streetlights along Labahita Street | Brgy. Longos | 989728 | 2019-03-11 | 2019-04-09 | 100% | 986680 |  | completed
4 | Proposed Installation of Ten (10) Sets of LED Streetlights along Acero Street | Brgy. Tugatog | 989728 | 2019-03-11 | 2019-04-09 | 100% | 985886 |  | completed
3 | Proposed Installation of Ten (10) Sets of LED Streetlights along Luna II Street | Brgy. San Agustin | 989728 | 2019-03-11 | 2019-04-09 | 100% | 985370 |  | completed
6 | Proposed Installation of Ten (10) Sets of LED Streetlights along Pineapple Road | Brgy. Potrero | 989728 | 2019-03-11 | 2019-04-09 | 100% | 985370 |  | completed
5 | Proposed Installation of Ten (10) Sets of LED Streetlights along Sarmiento Street | Brgy. Tinajeros | 989728 | 2019-03-11 | 2019-04-09 | 100% | 985026 |  | completed
2 | Proposed Installation of Ten (10) Sets of LED Streetlights along Mulawin Street | Brgy. Panghulo | 989728 | 2019-03-11 | 2019-04-09 | 100% | 984764 |  | completed
1 | Proposed Installation of Twenty-Five (25) Sets of LED Streetlights at Matadero Street and Magsaysay Extension | Brgy. San Agustin | 906254 | 2019-03-11 | 2019-04-24 | 100% | 901909 |  | completed
2 | Proposed Installation of Twenty-Five (25) Sets of LED Streetlights at Talipapa Street and Various Alleys | Brgy. Flores | 906254 | 2019-03-11 | 2019-04-24 | 100% | 901888 |  | completed
1 | Proposed Installation of Nine (9) Sets of LED Streetlights along Narra Street | Brgy. Panghulo | 888912 | 2019-03-11 | 2019-04-09 | 100% | 884085 |  | completed
2 | Proposed Installation of Six (6) Sets of LED Streetlights along Asogue Street and Three (3) Sets of LED Streetlights along Ganja Street | Brgy. Tugatog | 888912 | 2019-03-11 | 2019-04-09 | 100% | 884085 |  | completed
3 | Proposed Installation of Eight (8) Sets of LED Streetlights along Crispin Street | Brgy. Tinajeros | 790489 | 2019-03-11 | 2019-04-09 | 100% | 786162 |  | completed
6 | Proposed Installation of Eight (8) Sets of LED Streetlights along Dizon Street | Brgy. Tinajeros | 790489 | 2019-03-11 | 2019-04-09 | 100% | 786162 |  | completed
5 | Proposed Installation of Eight (8) Sets of LED Streetlights at Mabolo Street and Camachile Street | Brgy. Potrero | 790489 | 2019-03-11 | 2019-04-09 | 100% | 785904 |  | completed
7 | Proposed Installation of Eight (8) Sets of LED Streetlights at Anonas Street and Orange Street | Brgy. Potrero | 790489 | 2019-03-11 | 2019-04-09 | 100% | 785904 |  | completed
1 | Proposed Installation of Eight (8) Sets of LED Streetlights along Burgos Street Phase II | Brgy. Concepcion | 790489 | 2019-03-11 | 2019-04-09 | 100% | 785743 |  | completed
2 | Proposed Installation of Eight (8) Sets of LED Streetlights at Oro Street and Zinc Street | Brgy. Tugatog | 790489 | 2019-03-11 | 2019-04-09 | 100% | 785743 |  | completed
4 | Proposed Installation of Eight (8) Sets of LED Streetlights at Guyabano Street and Macopa Street | Brgy. Potrero | 790489 | 2019-03-11 | 2019-04-09 | 100% | 785710 |  | completed
42 | Proposed Installation of Twenty (20) Sets of LED Streetlights along P. Concepcion Street | Brgy. Tugatog | 724711 | 2019-03-29 | 2019-05-12 | 100% | 720234 |  | completed
1 | Proposed Installation of Seven (7) Sets of LED Streetlights along Hasa-Hasa Alley | Brgy. Longos | 691141 | 2019-03-11 | 2019-04-09 | 100% | 687010 |  | completed
1 | Proposed Installation of Thirteen (13) Sets of LED Streetlights along University Avenue Extension | Brgy. Potrero | 471691 | 2019-03-11 | 2019-04-09 | 100% | 466991 |  | completed
1 | Proposed Installation of Four (4) Sets of LED Streetlights along Espiritu Street | Brgy. Panghulo | 394948 | 2019-03-11 | 2019-04-09 | 100% | 390553 |  | completed
1 | Proposed Installation of Eight (8) Sets of LED Streetlights at Atis Street (Portion) and Guyabano Street (Portion) | Brgy. Potrero | 289866 | 2019-03-11 | 2019-04-09 | 100% | 285945 |  | completed
| Proposed Installation of Thirty - Two (32) Sets of LED Streetlights along P. Aquino Avenue | Brgys. Longos & Tonsuya | 3177184 | 2019-03-29 | 2019-05-12 | 100% | 3172621 |  | completed
| Proposed Installation of Sixteen (16) Sets of LED Streetlights along C-4 Road | Brgy. Longos | 2256828 | 2019-04-02 | 2019-05-01 | 100% | 2253338 |  | completed
| Proposed Installation of Twenty - Two (22) Sets of LED Streetlights along Rodriguez II Street | Brgy. Dampalit | 2184534 | 2019-03-29 | 2019-05-12 | 100% | 2180031 |  | completed
3 | Proposed Installation of Fifty - Eight (58) Sets of LED Streetlights at Samson Street and Various Alleys | Brgy. Baritan | 2105048 | 2019-03-11 | 2019-04-24 | 100% | 2100848 |  | completed
| Proposed Installation of Twenty - One (21) Sets of LED Streetlights along Valdez Street & Valdez Extension | Brgy. Catmon | 2084466 | 2019-03-29 | 2019-05-12 | 100% | 2081245.7 |  | completed
| Proposed Installation of Nineteen (19) Sets of LED Streetlights along Ma. Leni Street | Brgy. Hulong Duhat | 1885856 | 2019-04-02 | 2019-05-01 | 100% | 1882415 |  | completed
| Proposed Installation of Nineteen (19) Sets of LED Streetlights along Adante Street | Brgy. Tañong | 1885856 | 2019-03-29 | 2019-04-27 | 100% | 1880876.03 |  | completed
| Proposed Installation of Seventeen (17) Sets of LED Streetlights along R. Diaz Street | Brgy. Dampalit | 1687937 | 2019-04-02 | 2019-05-01 | 100% | 1683434 |  | completed
| Proposed Installation of Sixteen (16) Sets of LED Streetlights along Doña Juana Street | Brgy. Dampalit | 1588701 | 2019-03-29 | 2019-04-27 | 100% | 1585519 |  | completed
| Proposed Installation of Fourteen (14) Sets of LED Streetlights along Villanueva Street | Brgy. Tonsuya | 1389363 | 2019-03-29 | 2019-04-27 | 100% | 1384848 |  | completed
| Proposed Installation of Thirteen (13) Sets of LED Streetlights along Rivera Street | Brgy. Tañong | 1290411 | 2019-03-29 | 2019-04-27 | 100% | 1285780.04 |  | completed
| Proposed Installation of Thirty - Two (32) Sets of LED Streetlights at Alleys along C. Perez Street | Brgy. Tonsuya | 1253673 | 2019-03-29 | 2019-05-12 | 100% | 1249645 |  | completed
| Proposed Installation of Twelve (12) Sets of LED Streetlights along Gen. Borromeo Street Phase II | Brgy. Longos | 1190539 | 2019-04-02 | 2019-05-01 | 100% | 1186894 |  | completed
| Proposed Installation of Twelve (12) Sets of LED Streetlights along F. Nicolas Street | Brgy. Niugan | 1190539 | 2019-03-29 | 2019-07-26 | 100% | 1185957 |  | completed
| Proposed Installation of Eleven (11) Sets of LED Streetlights at Alley along Herrera Street | Brgy. Ibaba | 1092331 | 2019-03-29 | 2019-04-27 | 100% | 1088679.5 |  | completed
| Proposed Installation of Ten (10) Sets of LED Streetlights at Main Street & Side Street | Brgy. Tañong | 992354 | 2019-03-29 | 2019-07-26 | 100% | 988206.91 |  | completed
| Proposed Installation of Twenty - Five (25) Sets of LED Streetlights at Sulucan St., Milagrosa Street and Alley | Brgy. Hulong Duhat | 979347 | 2019-03-29 | 2019-05-12 | 100% | 974821 |  | completed
| Proposed Installation of Twenty - Five (25) Sets of LED Streetlights at L. Tuazon Street, Eusebio Street, A. Cruz Street, D. Marcelo Street & Sta. Rita Street (Portion) | Brgy. Baritan | 979347 | 2019-03-29 | 2019-05-12 | 100% | 974714 |  | completed
| Proposed Installation of Nine (9) Sets of LED Streetlights along Gil Pascual Street | Brgy. Hulong Duhat | 893508 | 2019-03-29 | 2019-04-27 | 100% | 889574 |  | completed
| Proposed Installation of Nine (9) Sets of LED Streetlights along Gulayan Street Phase III | Brgy. Catmon | 893508 | 2019-03-29 | 2019-04-27 | 100% | 889287.53 |  | completed
| Proposed Installation of Eight (8) Sets of LED Streetlights along Kagitingan Street Phase II | Brgy. Muzon | 794559 | 2019-03-29 | 2019-04-27 | 100% | 791106 |  | completed
| Proposed Installation of Eight (8) Sets of LED Streetlights along Ilang-Ilang Street | Brgy. Baritan | 794559 | 2019-03-29 | 2019-04-27 | 100% | 791106 |  | completed
| Proposed Installation of Eight (8) Sets of LED Streetlights at Mauricia Street, Sioson Street & Jose Street | Brgy. Niugan | 794559 | 2019-04-02 | 2019-05-01 | 100% | 790131 |  | completed
| Proposed Installation of Eight (8) Sets of LED Streetlights along Ortega Street Phase II | Brgy. Tonsuya | 794559 | 2019-03-29 | 2019-04-27 | 100% | 790131 |  | completed
| Proposed Installation of Eight (8) Sets of LED Streetlights along F. Sevilla Boulevard | Brgy. Tañong | 794559 | 2019-04-02 | 2019-05-01 | 100% | 789996 |  | completed
| Proposed Installation of Eight (8) Sets of LED Streetlights along Del Rosario Street Phase I | Brgy. Dampalit | 794559 | 2019-03-29 | 2019-04-27 | 100% | 789684 |  | completed
| Proposed Installation of Seven (7) Sets of LED Streetlights along Talabahan Street | Brgy. Baritan | 694684 | 2019-03-29 | 2019-04-27 | 100% | 690991 |  | completed
| Proposed Installation of Seven (7) Sets of LED Streetlights along Dagat-Dagatan Avenue (Portion) | Brgy. Longos | 694684 | 2019-03-29 | 2019-04-27 | 100% | 690295 |  | completed
| Proposed Installation of Seven (7) Sets of LED Streetlights along M. Aquino Street | Brgy. Niugan | 694684 | 2019-03-29 | 2019-05-12 | 100% | 689919.36 |  | completed
| Proposed Installation of Six (6) Sets of LED Streetlights along C. Perez Street (Portion) | Brgy. Tonsuya | 595734 | 2019-03-29 | 2019-04-27 | 100% | 593034 |  | completed
| Proposed Installation of Six (6) Sets of LED Streetlights along Tiangco Street | Brgy. Ibaba | 595734 | 2019-03-29 | 2019-04-27 | 100% | 592895.84 |  | completed
| Proposed Installation of Six (6) Sets of LED Streetlights along Sta. Rita Street | Brgy. Baritan | 595734 | 2019-03-29 | 2019-04-27 | 100% | 592110 |  | completed
| Proposed Installation of Six (6) Sets of LED Streetlights along Sta. Cruz Street going to Gervacio Street | Brgy. Hulong Duhat | 595734 | 2019-04-02 | 2019-05-01 | 100% | 591427 |  | completed
| Proposed Installation of Six (6) Sets of LED Streetlights along Escanilla Street Phase II | Brgy. Concepcion | 595734 | 2019-03-29 | 2019-04-27 | 100% | 591427 |  | completed
| Proposed Installation of Thirteen (13) Sets of LED Streetlights at P. Bautista Street & E. Aquino Street | Brgy. Niugan | 509295 | 2019-03-29 | 2019-04-27 | 100% | 505395.26 |  | completed
| Proposed Installation of Four (4) Sets of LED Streetlights along Mesina Street | Brgy. Tonsuya | 396911 | 2019-03-29 | 2019-04-27 | 100% | 392870 |  | completed
| Proposed Installation of Ten (10) Sets of LED Streetlights at Dulong Herrera Street (Portion) | Brgy. Ibaba | 391873 | 2019-03-29 | 2019-04-27 | 100% | 387250.04 |  | completed
| Proposed Installation of Ten (10) Sets of LED Streetlights at Kapt. Quimson Street (Portion) & Alley along Escanilla Street | Brgy. Concepcion | 391873 | 2019-03-29 | 2019-04-27 | 100% | 387221 |  | completed
| Proposed Installation of Two (2) Sets of LED Streetlights at R. Cruz Street (Portion) | Brgy. Dampalit | 299880 | 2019-03-29 | 2019-04-27 | 100% | 296867 |  | completed
| Proposed Installation of Thirty - Five (35) Sets of LED Streetlights along Gov. Pascual Avenue (Sisa Street to M.H. Del Pilar Street) | Brgys. Acacia & Tinajeros & Tonsuya | 3488806 | 2019-12-27 | 2020-02-09 |  | 3484356 |  | on going
| Proposed Installation of Twenty-Three (23) Sets of LED Streetlights along Celia Street (Crispin Street to Sisa Street) | Brgy. Tinajeros | 2293884 | 2019-12-27 | 2020-02-09 |  | 2288051 |  | on going
| Proposed Installation of Fifty-Six (56) Sets of LED Streetlights at Alley along Camia Street, Silonian Street, Remigio Street and Yanga Street | Brgy. Maysilo | 2193015 | 2019-12-17 | 2020-01-30 |  | 2188095 |  | on going
| Proposed Installation of Twenty (20) Sets of LED Streetlights at Jacinto Street and Burgos Street Phase II | Brgy. Concepcion | 1995143 | 2019-12-27 | 2020-02-09 |  | 1991412.68 |  | on going
| Proposed Installation of Nineteen (19) Sets of LED Streetlights along Nirvana Street | Brgy. Tugatog | 1894857 | 2019-12-27 | 2020-01-25 |  | 1889551 |  | on going
| Proposed Installation of Seventeen (17) Sets of LED Streetlights along Manapat Street | Brgy. Tañong | 1695446 | 2019-12-17 | 2020-01-15 |  | 1691094.32 |  | on going
| Proposed Installation of Seventeen (17) Sets of LED Streetlights along Leoño Street | Brgy. Tañong | 1695446 | 2019-12-17 | 2020-01-15 |  | 1691781 |  | on going
| Proposed Installation of Sixteen (16) Sets of LED Streetlights at M. Blas Street, M. Blas Extension & Talabahan Street | Brgy. Hulong Duhat | 1595902 | 2019-12-27 | 2020-01-25 |  | 1591132 |  | on going
| Proposed Installation of Thirty-Nine (39) Sets of LED Streetlights at Villangco Street, Custodio Street Alley, Matahong Extension, Katipunan Street Alley, Road I Street, Road 4 Street, Road 5 Street | Brgys. Santulan/ Concepcion/ Bayan-Bayanan/ San Agustin/ Dampalit | 1528026 | 2019-12-17 | 2020-01-30 |  | 1523853 |  | on going
| Proposed Installation of Fourteen (14) Sets of LED Streetlights along Flores St. (A.Bonifacio St. to Womens Club St.) | Brgy. Flores | 1396903 | 2019-12-17 | 2020-01-15 |  | 1392076.48 |  | on going
| Proposed Installation of Fourteen (14) Sets of LED Streetlights along N. Vicencio Street Phase II | Brgy. Niugan | 1396903 | 2019-12-27 | 2020-01-25 |  | 1391686 |  | on going
| Proposed Installation of Thirty - Five (35) Sets LED Streetlights at Pantihan III Street, Pantihan IV Street and Pantihan V Street | Brgy. Flores | 1371950 | 2019-12-17 | 2020-01-30 |  | 1366808 |  | on going
| Proposed Installation of Thirty - Five (35) Sets of LED Streetlights at Duhat Road, Orange Road & Maligaya Street | Brgy. Potrero | 1371950 | 2019-12-27 | 2020-02-09 |  | 1366472.46 |  | on going
| Proposed Installation of Thirteen (13) Sets of LED Streetlights along Paz Street (M.H. Del Pilar Street to Prosperidad Street) | Brgy. Tugatog | 1297058 | 2019-12-27 | 2020-01-25 |  | 1293466 |  | on going
| Proposed Installation of Thirteen (13) Sets of LED Streetlights along Libertad Street | Brgy. Tugatog | 1297058 | 2019-12-27 | 2020-01-25 |  | 1292210 |  | on going
| Proposed Installation of Twelve (12) Sets of LED Streetlights along Col. Espiritu Street | Brgy. Tinajeros | 1196875 | 2019-12-27 | 2020-01-25 |  | 1193382 |  | on going
| Proposed Installation of Eleven (11) Sets of LED Streetlights along Lanzones Street | Brgy. Potrero | 1096816 | 2019-12-17 | 2020-01-15 |  | 1092439 |  | on going
| Proposed Installation of Eleven (11) Sets of LED Streetlights along M.L. Quezon Street | Brgy. Tugatog | 1096816 | 2019-12-17 | 2020-01-15 |  | 1092439 |  | on going
| Proposed Installation of Eleven (11) Sets of LED Streetlights along Villarba Street | Brgy. Tinajeros | 1096816 | 2019-12-27 | 2020-01-25 |  | 1091894 |  | on going
| Proposed Installation of Ten (10) Sets of LED Streetlights along Mendiola Street | Brgy. Tonsuya | 997773 | 2019-12-27 | 2020-01-25 |  | 993225 |  | on going
| Proposed Installation of Nine (9) Sets of LED Streetlights along Juliana Street (Del Monte Street to River Side) | Brgy. Potrero | 897590 | 2019-12-17 | 2020-01-15 |  | 893842 |  | on going
| Proposed Installation of Eight (8) Sets of LED Streetlights along Pineapple Road (Phase II) | Brgy. Potrero | 797972 | 2019-12-17 | 2020-01-15 |  | 793344.89 |  | on going
| Proposed Installation of Eight (8) Sets of LED Streetlights at Industrial Road & Doña Juana Street (Phase II) | Brgy. Potrero | 797972 | 2019-12-17 | 2020-01-15 |  | 793344.89 |  | on going
| Proposed Installation of Seven (7) Sets of LED Streetlights along Pasco Street | Brgy. Tonsuya | 698304 | 2019-12-17 | 2020-01-15 |  | 694053 |  | on going
| Proposed Installation of Seven (7) Sets of LED Streetlights along Ignacio Street | Brgy. Panghulo | 698304 | 2019-12-17 | 2020-01-15 |  | 693327 |  | on going
| Proposed Installation of Six (6) Sets of LED Streetlights along Del Monte Street (Portion) | Brgy. Potrero | 598245 | 2019-12-17 | 2020-01-15 |  | 594491.37 |  | on going
| Proposed Installation of Six (6) Sets of LED Streetlights along P.S. Lacson Street | Brgy. San Agustin | 598245 | 2019-12-27 | 2020-01-25 |  | 593264.95 |  | on going
| Proposed Installation of Four (4) Sets of LED Streetlights along Anonas Street (Phase II) | Brgy. Potrero | 399017 | 2019-12-17 | 2020-01-15 |  | 396103 |  | on going
| Proposed Installation of Four (4) Sets of LED Streetlights along Cobre Street | Brgy. Tugatog | 399017 | 2019-12-17 | 2020-01-15 |  | 396103 |  | on going
| Proposed Installation of Four (4) Sets of LED Streetlights along B. Soriano Street | Brgy. Niugan | 399017 | 2019-12-17 | 2020-01-15 |  | 396103 |  | on going
| Proposed Installation of Four (4) Sets of LED Streetlights along Economia Street | Brgy. Tugatog | 399017 | 2019-12-17 | 2020-01-15 |  | 396103 |  | on going
| Proposed Installation of Four (4) Sets of LED Streetlights along Ligaya Street | Brgy. Tugatog | 399017 | 2019-12-27 | 2020-01-25 |  | 394967.1 |  | on going
| Proposed Installation of Four (4) Sets of LED Streetlights along San Diego Street | Brgy. Santulan | 399017 | 2019-12-27 | 2020-01-25 |  | 396103 |  | on going
1 | Proposed Installation of Eleven (11) Sets of LED Streetlights at Delos Santos One (1) and Delos Santos Two (2) Streets | Brgy. Tonsuya
2 | Proposed Installation of Eleven (11) Sets of LED Streetlights along Estanio Street | Brgy. Tugatog | [6 empty] | 0
#REF! | Proposed Installation of Six (6) Sets of LED Streetlights along Asogue Street and Three (3) Sets of LED Streetlights along Ganja Street | Brgy. Tugatog
| Proposed Installation of Eight (8) Sets of LED Streetlights along Burgos Street Phase II | Brgy. Concepcion
0
| Sub-Total |  | 128711679 |  |  |  | 128231521.35
| ECONOMIC DEVELOPMENT | [8 empty] | 34767811
1 | Proposed Upgrading / Rehabilitation of Sisa Extension (Portion) including drainage | Brgy. Tinajeros | 3290230 | 2019-04-02 | 2019-06-30 | 100% | 3285081 |  | completed
2 | Proposed Upgrading / Rehabilitation of Rosal Street & Camia Street including drainage | Brgy. Longos | 2108892 | 2019-04-29 | 2019-06-26 | 100% | 2102727 |  | completed
3 | Proposed Upgrading / Rehabilitation of various Alleys at Ugnatan Street including drainage | Brgy. Concepcion | 2012555 | 2019-03-28 | 2019-08-25 | 100% | 2008493 |  | completed
4 | Proposed Upgrading / Rehabilitation of various Alleys along Dulong Hernandez Street including drainage | Brgy. Catmon | 1978349 | 2019-03-29 | 2019-06-26 | 100% | 1974876 |  | completed
| Proposed Upgrading / Rehabilitation of Alley along Langaray Street at Block 9 including drainage | Brgy. Longos | 1757667 | 2019-05-24 | 2019-08-21 | 100% | 1750886 |  | completed
5 | Proposed Upgrading / Rehabilitation of Guekeko Street including drainage | Brgy. Baritan | 1696964 | 2019-04-02 | 2019-06-30 | 100% | 1691571 |  | completed
6 | Proposed Upgrading / Rehabilitation of various Alleys along Salmon Street at Block 46 including drainage | Brgy. Longos | 1692812 | 2019-03-29 | 2019-06-26 | 100% | 1687237 |  | completed
7 | Proposed Upgrading / Rehabilitation of Alley along Mesina Street including drainage | Brgy. Tinajeros | 1211249 | 2019-03-29 | 2019-05-27 | 100% | 1204564 |  | completed
8 | Proposed Upgrading / Rehabilitation of Kaybasco Street including drainage | Brgy. Tinajeros | 1024405 | 2019-03-29 | 2019-05-27 | 100% | 1018285 |  | completed
9 | Proposed Upgrading / Rehabilitation of Lopez Jaena Street including drainage | Brgy. Ibaba | 781653 | 2019-03-29 | 2019-05-27 | 100% | 775562 |  | completed
| Proposed Upgrading / Rehabilitation of Ilang-Ilang Street (Portion) including drainage | Brgy. Maysilo | 5496394 | 2019-11-25 | 2020-03-23 |  | 5488166 |  | on going
| Proposed Upgrading / Rehabilitation of various Alleys along Dulong Hernandez Street including drainage (Phase II) | Brgy. Catmon | 2803020 | 2019-11-25 | 2020-02-22 |  | 2798188 |  | on going
| Proposed Upgrading / Rehabilitation of various Alleys along S. Pascual Street including drainage | Brgy. San Agustin | 2607253 | 2019-11-25 | 2020-02-22 |  | 2602361 |  | on going
| Proposed Upgrading / Rehabilitation of Alley along Custodio Street including drainage | Brgy. Santulan | 2048039 | 2019-11-25 | 2020-02-07 |  | 2041317 |  | on going
| Proposed Upgrading / Rehabilitation of various Alleys at Liwayway Street including drainage | Brgy. Bayan-Bayanan | 1733037 | 2019-12-17 | 2020-03-15 |  | 1724266 |  | on going
| Proposed Upgrading / Rehabilitation of various Alleys between 1st Street & 2nd Street including drainage | Brgy. Tañong | 1445714 | 2019-11-25 | 2020-02-22 |  | 1441151 |  | on going
| Proposed Upgrading / Rehabilitation of Kasarinlan Street including drainage | Brgy. Muzon | 1079578 | 2019-11-25 | 2020-01-23 |  | 1071793 |  | on going
10
11
| Sub-Total |  | 34767811 |  |  |  | 34666524
ENVIRONMENTAL MANAGEMENT
| Proposed Greening / Beautification of Open Space along C-4 Road (Phase II) C-4 Road | Brgy. Tañong | 3030551 | 2019-12-17 | 2020-04-14 |  | 3022634 |  | on going
0
| Sub-Total |  | 3030551 |  |  |  | 3022634
| Grand Total |  | 166510041 |  |  |  | 165920679.35
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
|  | CYNTHIA P. RAMOS |  |  |  | HON. ANTOLIN A. ORETA III
|  | City Budget Officer |  |  |  | City Mayor