## 4th-qtr2019report
FDPP Form 6 - Trust Fund Utilization
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES
for the 4th QUARTER, CY 2019
Malabon City
Program or Project | Source Agency | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[6 empty] | % of Completion | Total Cost Incurred to Date
Construction of New Pagamutang Bayan ng Malabon | DPWH | F. Sevilla Blvd. San Agustin ,Malabon City | 142894901 | 2015-07-01 | 2016-04-30 | 98.61% | 140914875.85 |  | P148,125,000.00 is the actual amount received as of date (100% of MOA Total)
Improvement and maintenance of the Malabon City Bureau of Fire Protection Stations | Bureau Of Fire | Malabon City Fire Station-# 70 Gov. Pascual Ave. Potrero, Malabon City | 4850522.89 |  |  | 97.02% | 4706030 |  | Remaining fund balance is P144,492.89
Upgrading Production Capability of Malabon City Jail Bakery | DOST | Malabon City Jail | 334400 |  |  | 99.99% | 334370.54 |  | Project completed : has purchased supplies and equipment for the upgrading of Production Capability of Malabon City Jail Bakery: the unused amount of P 29.46 will be returned to DOST.
Local Health Systems Development AssistanceProgram | DOH-NCR | Malabon City | 1649380 | August 2018 | March 2019 | 82.43% | 1359649 |  | on going project
Construction of Pinagsabugan Linear Park in Barangay Longos(Local Government Support Fund -Assistance to Cities) | Bureau of the Treasury-NCR | Barangay Longos | 12094305 | March 11,2019 | November 6,2019 | 99.87% | 12078444 |  | project completed:unused amount of P 15,861.00 will be returned to Bureau of the Treasury.
Performance Challenge Fund -Procurement of medical equipment and machineries for the City of Malabon Health Care Facilities | DILG-NCR | Ospital ng Malabon | 5100000 |  |  | 99.96% | 5098000 |  | project completed:unused amount of P 2,000.00 will be returned to DILG.
Fund from DOH for the implementation of Medical Assistance Program for the indigent and poor patients in OSMAL(2nd) | DOH-NCR | Ospital ng Malabon | 1000000 | 2019-03-03 |  | 100% | 1000000 |  | Project completed
Management and Implementation of the CIPH CY 2014-2015 - "KALUSUGAN PANGKALAHATAN" | DOH-NCR | 21 Barangays | 805800 | November 2019 | March 2020 | 0% | 0 |  | For implementation (documents in process)
Fund from DOH for the implementation of Medical Assistance Program for the indigent and poor patients in OSMAL (3rd) | DOH-NCR | Ospital ng Malabon | 1980000 |  |  | 51.47% | 1019165.29 |  | on going project
Unified Access Quality Tertiary Education Act (UAQTEA) for the Implementation of the approved Qualification Maps (QM) no. 1 & 2 for the free TVET Program of CMPI | DOH-NCR | TESDA-NCR | 914820 | September 2,2019 |  | 67.23% | 615067 |  | on going project
Financial Assistance for medicines, medical supplies/devices & diagnostic test & other hospital care medical services & support to indigent, vulnerable & disadvantage patients. | Office of the President | Malasakit Center | 5000000 |  |  | 0% | 0 |  | for implementation
TOTAL |  |  | 176624128.89 |  |  |  | 167125601.68
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
CYNTHIA P. RAMOS |  |  | DINAH A. LAMSEN |  |  | HON. ANTOLIN A. ORETA III
City Budget Officer |  |  | City Accountant |  |  | City Mayor
0.94622
Note on D10: PC-71: Total construction cost plus EAO LGU