## TF FUR 4Q 2020
FDPP Form 6 - Trust Fund Utilization
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES
for the 4th QUARTER, CY 2020
Malabon City
Program or Project | Source Agency | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[6 empty] | % of Completion | Total Cost Incurred to Date
Improvement and maintenance of the Malabon City Bureau of Fire Protection Stations | Bureau Of Fire | Malabon City Fire Station-# 70 Gov. Pascual Ave. Potrero, Malabon City | 4850522.89 | February 14, 2018 | December 24,2018 | 97.02% | 4706030 |  | Remaining fund balance is P144,492.89
Local Health Systems Development AssistanceProgram | DOH-NCR | Malabon City | 1649380 | August 2018 | March 2019 | 98.8% | 1629649 |  | remaining fund balance is P19,731.00
Construction of Pinagsabugan Linear Park in Barangay Longos(Local Government Support Fund -Assistance to Cities) | Bureau of the Treasury-NCR | Barangay Longos | 12094305 | March 11,2019 | November 6,2019 | 99.87% | 12078444 |  | project completed, with a remaining fund balance of 15,861.00
Management and Implementation of the CIPH CY 2014-2015 - "KALUSUGAN PANGKALAHATAN" | DOH-NCR | 21 Barangays | 805800 | November 2019 | March 2020 | 99.98% | 805615 |  | has a remaining fund balance of P 185.00
Unified Access Quality Tertiary Education Act (UAQTEA) for the Implementation of the approved Qualification Maps (QM) no. 1 & 2 for the free TVET Program of CMPI | DOH-NCR | TESDA-NCR | 914820 | September 2,2019 | January 20,2020 | 99.38% | 909167 |  | has a remaining fund balance of P 5,653.00
Performance Challenge Fund -Procurement of mobile cars | DILG-NCR | Malabon City Police Station, Sansiangco St. Catmon, Malabon City | 3500000 | 2020-01-03 | November 16,2020 | 99.91% | 3497000 |  | Mobile cars was purchased last 11/16/2020 and the remaining fund balance of P 3,000.00 will be returned to BOT
Social Pension Indigent Senior Citizen for Senior Citizens of Malabon City for 1st to 4th quarter 2019 and 1st semester od CY 2020 | DSWD-NCR | 21 Barangays | 94305000 | June 3,2020 | June 22,2020 | 95.09% | 89676000 |  | remaining fund balance of P4,629,000.00 was returned under DV # 300-2009-147 with check no. 262169 dtd. 9/3/2020./ DSWD O.R. # 5234202 dts. 10/2/2020
Greening and Beautification of Letre Center Island, Sidewalk and Easement. | Bureau of the Treasury-NCR | Letre Road, Longos Malabon City | 18425901 | July 27, 2020 | February 21,2021 | 84.92% | 15646662.63 |  | 85% completed
Implementation of Supplementary Feeding Program to benefit 6,000 children in Malabon City | DSWD-NCR | Various Barangays | 2722500 | October 1, 2020 | October 30, 2020 | 99.83% | 2717988 |  | remaining fund balance of P4,512.00 was returned under D.V # 300-2012-0196 dated 12/14/2020
Financial assistance for the use of Medicines, medical supplies/devices & diagnostic test and other hospital test & other hospital care medical services & support at Ospital ng Malabon | Office of the President | Ospital Nang Malabon | 3988786.32 | October 2020 | December 17,2020 | 95.25% | 3799123.3 |  | remaining fund balance of P189,663.02 was returned under D.V # 300-2012-0200 dated 12/18/2020
Implementation of Medical Assistance to Indigent & Poor patients in Government hospitals | DOH-NCR | Ospital Nang Malabon | 10000000 |  |  | 0% | 0 |  | for implementation this coming January 2021
Transferred from GF- Local Government Support Fund for the Greening and Beautification of C-4 Road and Pampano St. Sidewalks at Longos, Malabon City | Bureau of the Treasury -NCR | C-4 Road and Pampano St. Sidewalks at Longos, Malabon | 18431816 | November 20, 2020 | July 24, 2021 | 14.98% | 2761817.01 |  | released of 15% mobilization fee
Calamity assistance for the affected families of Typhoon Ulysses | PCSO | Malabon City | 186000 |  |  | 0% | 0 |  | for implementation this coming January 2021
Recipient of the GSIS Adopt a Ligtas Covid Centers Program, a CSR bproject that supports RA 11469 known as "Bayanihan to Heal as One Act". | GSIS | Pagamutang Bayan ng Malabon | 500000 |  |  | 0% | 0 |  | for implementation up to December 18, 2021
Social Pension for Indigent Citizen of Malabon for 2nd sem CY 2020 | DSWD-NCR | 21 barangays at Malabon City | 48117000 |  |  | 0% | 0 |  | for implementation and 1st schedule of distribution is on January 26, 2021
TOTAL |  |  | 220491831.21 |  |  | 62.69% | 138227495.94
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
CYNTHIA P. RAMOS |  |  | DINAH A. LAMSEN |  |  | HON. ANTOLIN A. ORETA III
City Budget Officer |  |  | City Accountant |  |  | City Mayor