## jan-march2021
FDPP Form 6 - Trust Fund Utilization
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES
for the 1st QUARTER, CY 2021
Malabon City
Program or Project | Source Agency | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[6 empty] | % of Completion | Total Cost Incurred to Date
Improvement and maintenance of the Malabon City Bureau of Fire Protection Stations | Bureau of Fire | Malabon City Fire Station-# 70 Gov. Pascual Ave. Potrero, Malabon City | 4850522.89 | February 14, 2018 | December 24,2018 | 97.02% | 4706030 |  | Remaining fund balance is P144,492.89
Local Health Systems Development Assistance Program | DOH-NCR | Malabon City | 1649380 | August 2018 | March 2019 | 98.8% | 1629649 |  | the remaining fund balance of P19,731.00 is yet to be used by the City Health Department
Construction of Pinagsabugan Linear Park in Barangay Longos (Local Government Support Fund -Assistance to Cities) | Bureau of the Treasury-NCR | Barangay Longos | 12094305 | March 11,2019 | November 6,2019 | 99.87% | 12078444 |  | project completed, with a remaining fund balance of 15,861.00
Management and Implementation of the CIPH CY 2014-2015 - "KALUSUGAN PANGKALAHATAN" | DOH-NCR | 21 Barangays | 805800 | November 2019 | March 2020 | 99.98% | 805615 |  | the remaining fund balance of P 185.00 is yet to be used by the City Health Department
Unified Access Quality Tertiary Education Act (UAQTEA) for the Implementation of the approved Qualification Maps (QM) no. 1 & 2 for the free TVET Program of CMPI | DOH-NCR | TESDA-NCR | 914820 | September 2,2019 | January 20,2020 | 99.38% | 909167 |  | has a remaining fund balance of P 5,653.00
Performance Challenge Fund -Procurement of mobile cars | DILG-NCR | Malabon City Police Station, Sansiangco St. Catmon, Malabon City | 3500000 | 2020-01-03 | November 16,2020 | 99.91% | 3497000 |  | remaining fund balance of P3,000.00 is yet to be returned to BOT
Greening and Beautification of Letre Center Island, Sidewalk and Easement. | Bureau of the Treasury-NCR | Letre Road, Longos Malabon City | 18425901 | July 27, 2020 | February 21,2021 | 99.9% | 18407751 |  | 100% completed as of 2/23/2021. Remaining fund balance of P 18,150.00 is yet to be returned to BOT
Implementation of Medical Assistance to Indigent & Poor patients in Government hospitals | DOH-NCR | Ospital Nang Malabon | 10000000 | January 2021 |  | 12.8% | 1280391.61 |  | on going project
Transferred from GF- Local Government Support Fund for the Greening and Beautification of C-4 Road and Pampano St. Sidewalks at Longos, Malabon City | Bureau of the Treasury -NCR | C-4 Road and Pampano St. Sidewalks at Longos, Malabon | 18431816 | November 20, 2020 | July 24, 2021 | 48.95% | 9021720.33 |  | 2nd and partial (46%) payment
Calamity assistance for the affected families of Typhoon Ulysses | PCSO | Malabon City | 186000 | 2021-02-15 | 2021-02-16 | 100% | 186000 |  | With FUR submitted to CSWDD
Recipient of the GSIS Adopt a Ligtas Covid Centers Program, a CSR bproject that supports RA 11469 known as "Bayanihan to Heal as One Act". | GSIS | Pagamutang Bayan ng Malabon | 500000 |  |  | 0% | 0 |  | for implementation up to December 18, 2021
Social Pension for Indigent Citizen of Malabon for 2nd sem CY 2020 | DSWD-NCR | 21 barangays at Malabon City | 48117000 | 2021-01-22 | 2021-03-04 | 97.95% | 47133000 |  | Liquidated under ROD # 300-mdmg-21-003-01-003 dtd. 3/4/2021.The unused amt was returned to DSWD-NCR under O.R. #5234319 dtd. 3/19/2021
Financial assistance to LGU's affected by Typhoon Ulysses | Bureau of the Treasury -NCR | Malabon City | 2061353 |  |  | 0% | 0 |  | for implementation
4 month payment for active hazard duty pay (AHD) and/ or Special Risk allowancer (SRA) | DOH-CHD | Malabon City | 4762589.93 | January 28,2021 | February 11,2021 | 99.99% | 4762164.54 |  | FUR submitted to DOH, remaining fund balance oid P 425.39 was returned under DV # 300-2103-033 , check # 262236 dtd. 3/18/2021
Financial assistance for the services of 26 existsing Barangay Nutrition Scholars (BNS) for CY 2020 | National Nutrition Council-NCR | Barangay Health Center | 32300 | 2021-02-05 | 2021-02-11 | 100% | 32300 |  | project completed
Medical assistance for payment of medicines, medical services and other care to indigent patients | Office of the President | Ospital Nang Malabon | 5000000 | 2021-02-05 |  | 14.44% | 721947.27 |  | on going project
TOTAL |  |  | 131331787.82 |  |  | 80.08% | 105171179.75
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
CYNTHIA P. RAMOS |  |  | DINAH A. LAMSEN |  |  | HON. ANTOLIN A. ORETA III
City Budget Officer |  |  | City Accountant |  |  | City Mayor