## 2ND (for posting)
FDP Form 7 - 20% Development Fund Utilization
UTILIZATION OF THE 20% COMPONENT OF IRA FOR DEVELOPMENT PROJECTS
SECOND QUARTER, CY 2021
Province, City or Municipality : CITY GOVERNMENT OF MALABON
| Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[6 empty] | % of Completion | Total Cost Incurred to Date
| SOCIAL DEVELOPMENT | [8 empty] | 25448463.86
#REF! | Proposed Installation of 14 sets LED Streetlights at MRH Compound | Baritan | 1426944 | May 13, 2021 | June 11, 2021 | 100% |  |  | Completed (but not yet paid)
| Proposed Installation of 5 sets LED Streetlights along Hernandez Ext. | Catmon | 507981 | May 13, 2021 | June 11, 2021 | 100% |  |  | Completed (but not yet paid)
| Proposed Installation of 14 sets LED Streetlights along Doña Ines St. | Dampalit | 1426944 | May 13, 2021 | June 11, 2021 | 100% |  |  | Completed (but not yet paid)
| Proposed Installation of 12 sets LED Streetlights along Nora Victoria St. | Hulong Duhat | 1222069 | May 13, 2021 | June 11, 2021 | 100% | 1209392 |  | Completed
| Proposed Installation of 4 sets LED Streetlights along Marlon St. | Hulong Duhat | 415390 | May 13, 2021 | June 11, 2021 | 100% | 409835 |  | Completed
| Proposed Installation of 6 sets LED Streetlights along Paulo St. | Hulong Duhat | 611761 | May 13, 2021 | June 11, 2021 | 100% | 605547.62 |  | Completed
| Proposed Installation of 6 sets LED Streetlights along Allan St. | Hulong Duhat | 611761 | May 13, 2021 | June 11, 2021 | 100% | 605547.62 |  | Completed
| Proposed Installation of 6 sets LED Streetlights along Frederick St. | Hulong Duhat | 611761 | May 13, 2021 | June 11, 2021 | 100% | 605547.62 |  | Completed
| Proposed Installation of 10 sets LED Streetlights along Tanigue St. | Longos | 1019107 | May 13, 2021 | June 11, 2021 | 100% | 1009546 |  | Completed
| Proposed Installation of 21 sets LED Streetlights along Hiwas St. | Longos | 2136354 | May 13, 2021 | June 26, 2021 | 100% | 2117648 |  | Completed
| Proposed Installation of 33 sets LED Streetlights along Dalagang Bukid St. | Longos | 3361762 | May 13, 2021 | June 26, 2021 | 100% | 3329672 |  | Completed
| Proposed Installation of 11 sets LED Streetlights along Azucena St. | Longos | 1120691 | May 13, 2021 | June 11, 2021 | 100% | 1109629.08 |  | Completed
| Proposed Installation of 10 sets LED Streetlights along Mabolo St. (Gov. Pascual Ave. to Duhat Rd.) | Potrero | 1019107 | May 13, 2021 | June 11, 2021 | 100% | 1009546 |  | Completed
| Proposed Installation of 13 sets LED Streetlights along Riverside St. | Potrero | 1318768 | May 13, 2021 | June 11, 2021 | 100% | 1306136 |  | Completed
| Proposed Installation of 10 sets LED Streetlights along J.P. Bautista St. | Potrero | 1019107 | May 13, 2021 | June 11, 2021 | 100% | 1009546 |  | Completed
| Proposed Installation of 3 sets LED Streetlights along R. Santos St. | San Agustin | 305302 | May 13, 2021 | June 11, 2021 | 100% |  |  | Completed (but not yet paid)
| Proposed Installation of 3 sets LED Streetlights along Asinan St. | San Agustin | 305302 | May 13, 2021 | June 11, 2021 | 100% |  |  | Completed (but not yet paid)
| Proposed Installation of 7 sets LED Streetlights along Dela Cruz St. | Tinajeros | 708461 | May 13, 2021 | June 11, 2021 | 100% | 701255 |  | Completed
| Proposed Installation of 11 sets LED Streetlights along Concha St. | Tinajeros | 1120691 | May 13, 2021 | June 11, 2021 | 100% | 1109629.08 |  | Completed
| Proposed Installation of 7 sets LED Streetlights along Pacencia St. | Tugatog | 708461 | May 13, 2021 | June 11, 2021 | 100% |  |  | Completed (but not yet paid)
| Proposed Installation of 13 sets LED Streetlights along Progreso St. | Tugatog | 1318768 | May 13, 2021 | June 11, 2021 | 100% |  |  | Completed (but not yet paid)
| Proposed Installation of 9 sets LED Streetlights at Nadala St. and P. Cruz St. | Dampalit | 915817 | May 13, 2021 | June 11, 2021 | 100% |  |  | Completed (but not yet paid)
| Proposed Installation of 12 sets LED Streetlights at Don Arsenio St., Don Horacio St. and Doña Rufina St. | Dampalit | 1222069 | May 13, 2021 | June 11, 2021 | 100% |  |  | Completed (but not yet paid)
#REF! | Proposed Installation of 4 sets LED Streetlights along Robert St. | Hulong Duhat | 415390 | May 13, 2021 | June 11, 2021 | 100% | 409835 |  | Completed
#REF! | Proposed Installation of 8 sets LED Streetlights along Geoffrey St. | Hulong Duhat | 812243 | May 13, 2021 | June 11, 2021 | 100% | 804665.87 |  | Completed
| Proposed Installation of 7 sets LED Streetlights along Dennis St. | Hulong Duhat | 708461 | May 13, 2021 | June 11, 2021 | 100% | 701255 |  | Completed
| Proposed Installation of 3 sets LED Streetlights along Patrick St. | Hulong Duhat | 305302 | May 13, 2021 | June 11, 2021 | 100% | 301666.22 |  | Completed
| Proposed Installation of 3 sets LED Streetlights at Womens Club St. Portion | Hulong Duhat | 332937 | May 13, 2021 | June 11, 2021 | 100% |  |  | Completed (but not yet paid)
| Proposed Installation of 9 sets LED Streetlights along Salinas St. | Longos | 915817 | May 13, 2021 | June 11, 2021 | 100% | 905677 |  | Completed
| Proposed Installation of 23 sets LED Streetlights along Alupihang Dagat St. | Longos | 2339317 | May 13, 2021 | June 26, 2021 | 100% | 2314546 |  | Completed
| Proposed Installation of 22 sets LED Streetlights along Mango Road | Potrero | 2231141 | May 13, 2021 | June 26, 2021 | 100% | 2210558.75 |  | Completed
| Proposed Installation of 7 sets LED Streetlights along Nangka Road Phase II | Potrero | 708461 | May 13, 2021 | June 11, 2021 | 100% | 701255 |  | Completed
| Proposed Installation of 6 sets LED Streetlights at Mac Arthur Hi-Way Portion (from Riverside St. to Tullahan Bridge) | Potrero | 660080 | May 13, 2021 | June 11, 2021 | 100% |  |  | Completed (but not yet paid)
| Proposed Installation of 7 sets LED Streetlights along Progalidad St. | Tugatog | 708461 | May 13, 2021 | June 11, 2021 | 100% |  |  | Completed (but not yet paid)
| Proposed Installation of 9 sets LED Streetlights along Roque St. | Tugatog | 915817 | May 13, 2021 | June 11, 2021 | 100% |  |  | Completed (but not yet paid)
| Proposed Installation of 32 sets LED Streetlights at Alley along Bernardo II St., Constantino St., Geukeko St. and Pescadores St. Phase II | Baritan | 1204400 | May 13, 2021 | June 26, 2021 | 100% |  |  | Completed (but not yet paid)
| Proposed Installation of 26 sets LED Streetlights at alley along Gen. Luna St., Escanilla St. and Burgos St. | Concepcion | 970645 | May 13, 2021 | June 26, 2021 | 100% | 960528 |  | Completed
#REF! | Proposed Installation of 11 sets LED Streetlights at Various Alley along Esguerra St. | Flores | 440766 | May 13, 2021 | June 11, 2021 | 100% |  |  | Completed (but not yet paid)
| Proposed Installation of 7 sets Streetlights at Alley along Gen. Luna St. (Interior) | Ibaba | 255261 | May 13, 2021 | June 11, 2021 | 100% |  |  | Completed (but not yet paid)
| Proposed Installation of 20 sets LED Streetlights at alley along Tiangko St., Jacinto St., Vidal St. and Camus St. | Ibaba | 801922 | May 13, 2021 | June 26, 2021 | 100% |  |  | Completed (but not yet paid)
| Proposed Installation of 12 sets LED Streetlights at Alley along Gen. Luna St. and C. Arellano St. | San Agustin | 421167 | May 13, 2021 | June 11, 2021 | 100% |  |  | Completed (but not yet paid)
| Malabon Community Pantry (Malabon Kontra Gutom) | City Wide | 38271546 | [5 empty] | Bidded
| ECONOMIC DEVELOPMENT | [8 empty] | 616398
| Proposed Upgrading / Rehabilitation of Samson St. (Portion) including Drainage | Baritan | 1886251 | May 13, 2021 | July 26, 2021 | 70% |  |  | Ongoing
| Proposed Upgrading / Rehabilitation of Various Alleys at Rodriguez St. including Drainage | Bayan-Bayanan | 622538 | May 13, 2021 | July 11, 2021 | 100% | 616398 |  | Completed
| Proposed Rehabilitation of Kapitan Bernardo St. including Drainage | Concepcion | 5982391 | May 13, 2021 | September 9, 2021 | 60% |  |  | Ongoing
| Proposed Rehabilitation of Flores St. (Portion) including Drainage | Flores | 4932767 | May 13, 2021 | September 9, 2021 | 60% |  |  | Ongoing
| Proposed Upgrading / Rehabilitation of Various Alleys along Maya-Maya St. and Pampano St. at Blk. 43 & 44 including Drainage | Longos | 3676404 | May 13, 2021 | August 10, 2021 | 60% |  |  | Ongoing
| Proposed Upgrading / Rehabilitation of Kaunlaran St. (Portion) including Drainage | Muzon | 2641540 | May 13, 2021 | July 26, 2021 | 80% |  |  | Ongoing
| Proposed Upgrading / Rehabilitation of Various Alley between 1st St., 2nd St. and 3rd St. including Drainage | Tañong | 2238802 | May 13, 2021 | August 10, 2021 | 50% |  |  | Ongoing
| Proposed Upgrading / Rehabilitation of Delos Santos 1 St. including Drainage | Tonsuya | 5321039 | May 13, 2021 | September 9, 2021 | 60% |  |  | Ongoing
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
| (Signed) |  | (Signed)
| MAILA R. CAINGLES |  | HON. ANTOLIN A. ORETA III
| OIC - City Budget Department |  | City Mayor
26064861.86