## 2Q 2021
FDPP Form 6 - Trust Fund Utilization
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES
for the 2nd QUARTER, CY 2021
Malabon City
Program or Project | Source Agency | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[6 empty] | % of Completion | Total Cost Incurred to Date
Improvement and maintenance of the Malabon City Bureau of Fire Protection Stations | Bureau of Fire | Malabon City Fire Station-# 70 Gov. Pascual Ave. Potrero, Malabon City | 4850522.89 | February 14, 2018 | December 24,2018 | 97.02% | 4706030 |  | Remaining fund balance is P144,492.89
Local Health Systems Development Assistance Program | DOH-NCR | Malabon City | 1649380 | August 2018 | March 2019 | 98.8% | 1629649 |  | the remaining fund balance of P19,731.00 is yet to be used by the City Health Department
Construction of Pinagsabugan Linear Park in Barangay Longos(Local Government Support Fund -Assistance to Cities) | Bureau of the Treasury-NCR | Barangay Longos | 12094305 | March 11,2019 | November 6,2019 | 99.87% | 12078444 |  | remaining fund balance of P15,861.00 was returned under D.V # 300-2104-063 with check 3 262265 dtd. 4/27/2021,BOT O.R #7062258 dtd. 4/30/2021
Management and Implementation of the CIPH CY 2014-2015 - "KALUSUGAN PANGKALAHATAN" | DOH-NCR | City Health Department | 805800 | June 25,2020 | 2021-12-01 | 22.06% | 177777.25 |  | Ongoing project
Unified Access Quality Tertiary Education Act (UAQTEA) for the Implementation of the approved Qualification Maps (QM) no. 1 & 2 for the free TVET Program of CMPI | DOH-NCR | TESDA-NCR | 914820 | September 2,2019 | January 20, 2020 | 99.38% | 909167 |  | has a remaining fund balance of P 5,653.00, yet to be returned to TESDA
Performance Challenge Fund -Procurement of mobile cars | DILG-NCR | Malabon City Police Station, Sansiangco St. Catmon, Malabon City | 3500000 | 43833 | November 16,2020 | 99.91% | 3497000 |  | The remaining fund balance of P 3,000 was returned under check # 262258 dtd. 4/20/2021/ O.R. # 7062257 dtd 4/30/2021
Greening and Beautification of Letre Center Island, Sidewalk and Easement. | Bureau of the Treasury-NCR | Letre Road, Longos Malabon City | 18425901 | July 27, 2020 | February 21,2021 | 99.9% | 18407751 |  | The remaining fund balance of P 18,150.00 was returned to BOT under check # 262288 dtd 6/3/2021, OR # 7062391 dtd. 6/4/2021
Greening and Beautification of C4 Road and Pampano St. Sidewalks located at Barangay Longos. | Bureau of the Treasury-NCR | C4 Road & Pampano St. | 18431816 | February 2021 | April 27, 2021 | 99.89% | 18412113.4 |  | The remaining fund balance of P 19,702.60 was returned to BOT under check # 262287 dtd 6/3/2021, OR # 7062391 dtd. 6/4/2021
Implementation of Medical Assistance to Indigent & Poor patients in Government hospitals | DOH-NCR | Ospital ng Malabon | 10000000 | January 2021 | 2021-12-01 | 39.59% | 3959003.36 |  | Ongoing project
Local Government Support Fund for the Greening and Beautification of C-4 Road and Pampano St. Sidewalks at Longos, Malabon City | Bureau of the Treasury -NCR | C-4 Road and Pampano St. Sidewalks at Longos, Malabon | 18431816 | November 20, 2020 | July 24, 2021 | 99.89% | 18412113.4 |  | The remaining fund balance of P 19,702.60 was returned to BOT under check # 262287 dtd 6/30/2021, O.R # 7062390 dtd. 6/4/2021
Recipient of the GSIS Adopt a Ligtas COVID Centers Program, a CSR bproject that supports RA 11469 known as "Bayanihan to Heal as One Act". | GSIS | Pagamutang Bayan ng Malabon | 500000 | April 15,2021 | June 14,2021 | 99.85% | 499263 |  | Remaining fund balance of P737.00 is yet to be returned to GSIS
Financial assistance to LGU's affected by Typhoon Ulysses | Bureau of the Treasury -NCR | Malabon City | 2061353 | July 15, 2021 | September 9,2021 | 0% | 0 |  | with issued CAF dated May 18, 2021 for the upgrading/ rehabilitation of Alley along Rivera St. including drainage
4 month payment for active hazard duty pay (AHD) and/ or Special Risk allowancer (SRA) | DOH-CHD | Malabon City | 4762589.93 | January 28,2021 | February 11,2021 | 99.99% | 4762164.54 |  | FUR submitted to DOH, remaining fund balance of P 425.39 will be returned via DV # 300-2103-033 , check # 262236 dtd. 3/18/2021
Medical assistance for payment of medicines, medical services and other care to indigent patients | Office of the President | Ospital ng Malabon | 8781281.9 | February 05, 2021 | 2021-12-01 | 49.93% | 4384067.82 |  | Ongoing project
2021 Disaster Reduction and Rehabilitation Assistance Program-Financial Assistance for the recovery and reconstruction of economy and livelihood in LGU's affected by Taal Volcano Eruption and Typhoon | Bureau of the Treasury -NCR | Alley bestween Adante & Rivera St. & Drainage | 973439 | July 15, 2021 | September 9,2021 | 0% | 0 |  | with issued CAF dated May 18, 2021 for the upgrading/rehabilitation of Alley between Adante & Rivera St. and drainage leading to Rivera pumping Station
Financial Assistance to Cities and Municipalities in the National Capital Region(NCR)and in the provinces of Bulacan,Cavite,Laguna & Rizal, collectively known as the "NCR PLUS" | Bureau of the Treasury -NCR | various barangays in Malabon City | 300175000 | April 7,2021 | June 2021 | 100% | 300175000 |  | for Liquidation
Grant of COVID-19 Special Risk Allowance (SRA) for Health Workers catering service/ in contact with COVID-19 patients for the period covered December 19, 2020 to June 30, 2021. | DOH-NCR | Malabon City | 8782436.25 |  |  | 0% | 0 |  | for implementation
TOTAL |  |  | 415140460.97 |  |  | 94.43% | 392009543.77
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
MAILA R. CAINGLES |  |  | DINAH A. LAMSEN |  |  | HON. ANTOLIN A. ORETA III
OIC - City Budget Department |  |  | City Accountant |  |  | City Mayor