## july-sept2021
FDPP Form 6 - Trust Fund Utilization
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES
for the 3rd QUARTER, CY 2021
Malabon City
Program or Project | Source Agency | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[6 empty] | % of Completion | Total Cost Incurred to Date
Improvement and maintenance of the Malabon City Bureau of Fire Protection Stations | Bureau of Fire | Malabon City Fire Station-# 70 Gov. Pascual Ave. Potrero, Malabon City | 4850522.89 | February 14, 2018 | December 24,2018 | 97.02% | 4706030 |  | Remaining fund balance is P144,492.89 | 144492.89 |  | date started is the date of receipt
Local Health Systems Development Assistance Program | DOH-NCR | Malabon City | 1649380 | August 2018 | 2021-07-27 | 99.99% | 1649294.25 |  | the remaining fund balance of P 85.75 |  |  | to be used by health dept. |  | 14724.25
Management and Implementation of the CIPH CY 2014-2015 - "KALUSUGAN PANGKALAHATAN" | DOH-NCR | City Health Department | 805800 | June 25,2020 | 2021-12-01 | 22.06% | 177777.25 |  | Ongoing project |  | verify amount blance
Unified Access Quality Tertiary Education Act (UAQTEA) for the Implementation of the approved Qualification Maps (QM) no. 1 & 2 for the free TVET Program of CMPI | DOH-NCR | TESDA-NCR | 914820 | September 2,2019 | January 20, 2020 | 98.43% | 900439.78 |  | has a remaining fund balance of P 14,380.22, yet to be returned to TESDA
Implementation of Medical Assistance to Indigent & Poor patients in Government hospitals | DOH-NCR | Ospital ng Malabon | 10000000 | January 2021 | 2021-12-01 | 70.97% | 7097414.37 |  | Ongoing project
Recipient of the GSIS Adopt a Ligtas COVID Centers Program, a CSR bproject that supports RA 11469 known as "Bayanihan to Heal as One Act". | GSIS | Pagamutang Bayan ng Malabon | 500000 | April 15,2021 | June 14,2021 | 99.85% | 499263 |  | Remaining fund balance of P737.00 yet to be returned to GSIS
Financial assistance to LGU's affected by Typhoon Ulysses | Bureau of the Treasury -NCR | Malabon City | 2061353 | July 15, 2021 | September 9,2021 | 0% | 0 |  | Billing in process for the upgrading/ rehabilitation of Alley along Rivera St. including drainage
Medical assistance for payment of medicines, medical services and other care to indigent patients | Office of the President | Ospital ng Malabon | 12541274.72 | February 05, 2021 | 2021-12-01 | 80.77% | 10129370.72 |  | Ongoing project
2021 Disaster Reduction and Rehabilitation Assistance Program-Financial Assistance for the recovery and reconstruction of economy and livelihood in LGU's affected by Taal Volcano Eruption and Typhoon | Bureau of the Treasury -NCR | Alley bestween Adante & Rivera St. & Drainage | 973439 | July 15, 2021 | September 9,2021 | 0% | 0 |  | Billing in process for the upgrading/rehabilitation of Alley between Adante & Rivera St. and drainage leading to Rivera pumping Station
Financial Assistance to Cities and Municipalities in the National Capital Region(NCR)and in the provinces of Bulacan,Cavite,Laguna & Rizal, collectively known as the "NCR PLUS" | Bureau of the Treasury -NCR | various barangays in Malabon City | 300175000 | April 7,2021 | June 2021 | 100% | 300175000 |  | Liquidated under Report of Disbursement # 300-21-007-012 dated 7/1/2021
Grant of COVID-19 Special Risk Allowance (SRA) for Health Workers catering service/ in contact with COVID-19 patients for the period covered December 19, 2020 to June 30, 2021. | DOH-NCR | Malabon City | 8782436.25 | August 21,2021 | September 2021 | 54.88% | 4819487.62 |  | with partial liquidation under ROD Report # 300-jpb-2109-001 dated 9/15/2021
Nursery and Green Space at Atis Barangay Potrero and Greeening and Beautification of C-4 Raod, Eastment and Sidewalk at Barangay Tañong. | Bureau of the Treasury-NCR | Barangay Potrero and Tañong | 17500000 | [5 empty] | Barangay Potrero (7,337,896.00)-bidded already, waiting for Notice to Proceed Barangay Potrero (10,162,104.00) for bidding
Implementation of Medical Assistance to Indigent & Poor patients in Government hospitals | DOH-NCR | Ospital ng Malabon | 7850000 | [5 empty] | for implementation
Financial Assistance to low income population of various Local Government Units (LGUs) in the National Capital Region | Bureau of the Treasury -NCR | 21 Barangay in Malabon City | 307004000 | August 11,2021 | August 30,2021 | 100% | 307004000 |  | for liquidation
TOTAL |  |  | 675608025.86 |  |  | 94.31% | 637158076.99
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
MAILA R. CAINGLES |  |  | DINAH A. LAMSEN |  |  | HON. ANTOLIN A. ORETA III
OIC - City Budget Department |  |  | City Accountant |  |  | City Mayor
#REF!
1649380
805800
1000000
31200
3820085.67
335048000
3779038.04
346133503.71