## oct-dec2021
FDPP Form 6 - Trust Fund Utilization
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES
for the 4th QUARTER, CY 2021
Malabon City
Program or Project | Source Agency | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[6 empty] | % of Completion | Total Cost Incurred to Date
Improvement and maintenance of the Malabon City Bureau of Fire Protection Stations | Bureau of Fire | Malabon City Fire Station-# 70 Gov. Pascual Ave. Potrero, Malabon City | 4850522.89 | February 14, 2018 | December 24,2018 | 97.02% | 4706030 |  | Remaining fund balance is P144,492.89
Local Health Systems Development Assistance Program | DOH-NCR | Malabon City | 1649380 | August 2018 | 2021-07-27 | 99.99% | 1649294.25 |  | unexpended balance of P85.75 was returned under check no. 262388 dtd.11/26/2021, DOH O.R # 2516085 dtd. 12/3/2021
Management and Implementation of the CIPH CY 2014-2015 - "KALUSUGAN PANGKALAHATAN" | DOH-NCR | City Health Department | 805800 | June 25,2020 | 2021-12-01 | 22.06% | 177777.25 |  | Remaining fund balance of P628,022.75 is yet to be implemted by City Health Department
Unified Access Quality Tertiary Education Act (UAQTEA) for the Implementation of the approved Qualification Maps (QM) no. 1 & 2 for the free TVET Program of CMPI | DOH-NCR | TESDA-NCR | 914820 | September 2,2019 | January 20, 2020 | 98.43% | 900439.78 |  | the amount of P14,380.22 is yet to be returned by CMPI to TESDA(with prepared DV # 300-2111-195 dated 11/24/2021)
Implementation of Medical Assistance to Indigent & Poor patients in Government hospitals | DOH-NCR | Ospital ng Malabon | 17850000 | January 2021 | 2021-12-01 | 72.52% | 12945090.77 |  | Ongoing project with available fund balance of P4,904,909.23
Recipient of the GSIS Adopt a Ligtas COVID Centers Program, a CSR bproject that supports RA 11469 known as "Bayanihan to Heal as One Act". | GSIS | Pagamutang Bayan ng Malabon | 500000 | April 15,2021 | June 14,2021 | 99.85% | 499263 |  | unexpended balance was returnedto GSIS under check no. 262385 dtd.11/22/2021, GSIS O.R.# 7550055723 dtd. 12/6/2021
Financial assistance to LGU's affected by Typhoon Ulysses | Bureau of the Treasury -NCR | Malabon City | 2061353 | July 15, 2021 | September 9,2021 | 99.04% | 2041487 |  | 1st and Final ( 100% ) Payment under check # 262398 dtd. 12/6/2021. unexpended amount of P19,866.00 is yet to be returned.
Medical assistance for payment of medicines, medical services and other care to indigent patients | Office of the President | Ospital ng Malabon | 16294734.7 | February 05, 2021 | 2021-12-01 | 81.11% | 13217451.18 |  | Ongoing project with available fund balance of P2,155,236.12
2021 Disaster Reduction and Rehabilitation Assistance Program-Financial Assistance for the recovery and reconstruction of economy and livelihood in LGU's affected by Taal Volcano Eruption and Typhoon( | Bureau of the Treasury -NCR | Alley bestween Adante & Rivera St. & Drainage | 973439 | July 15, 2021 | September 9,2021 | 99% | 963695 |  | 1st and Final ( 100% ) Payment under check # 262397 dtd. 12/6/2021. unexpended amount of P9,744.00 is yet to be returned.
Grant of COVID-19 Special Risk Allowance (SRA) for Health Workers catering service/ in contact with COVID-19 patients for the period covered December 19, 2020 to June 30, 2021. | DOH-NCR | Malabon City | 8782436.25 | August 21,2021 | September 2021 | 100% | 8782394.61 |  | Unused amount of P41.64 was returned under DOH O.R.# 2515741 dated 11/16/2021
Nursery and Green Space at Atis Barangay Potrero and Greeening and Beautification of C-4 Raod, Eastment and Sidewalk at Barangay Tañong. | Bureau of the Treasury-NCR | Barangay Potrero | 7337896 | November 15,2021 | February 19,2022 | 29.7% | 2179630.81 |  | 1st and partial ( 30.02% ) Payment made under check # 262400 dtd. 12/14/2021.
Greeening and Beautification of C-4 Raod, Eastment and Sidewalk at Barangay Tañong. | Bureau of the Treasury-NCR | Barangay Tañong | 10162104 | December 14,2021 | June 11,2022 |  |  |  | 40% work accomplished, yet to be paid
Financial Assistance to low income population of various Local Government Units (LGUs) in the National Capital Region | Bureau of the Treasury -NCR | 21 Barangay in Malabon City | 307004000 | August 11,2021 | August 30,2021 | 100% | 307004000 |  | Fund Utilization Report was submitted to concerned Department and DILG
Financial grant for the implementation of "Enhanced Kadiwa ni Ani at Kita Financial Grant Assistance Program. | Department of Agriculture | Nuestra Señora Credit Cooperative & Ang Palengke Natin Service Cooperative at Malabon City | 2000000 |  |  | 100% | 2000000 |  | Have released check nos.262415 & 262416 at 1,000,000.00 each, both dated Dec. 31,2021
TOTAL |  |  | 381186485.84 |  |  | 93.67% | 357066553.65
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
MAILA R. CAINGLES |  |  | DINAH A. LAMSEN |  |  | HON. ANTOLIN A. ORETA III
OIC - City Budget Department |  |  | City Accountant |  |  | City Mayor