## jan-march2022
FDPP Form 6 - Trust Fund Utilization
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES
for the 1st QUARTER, CY 2022
Malabon City
Program or Project | Source Agency | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[6 empty] | % of Completion | Total Cost Incurred to Date
Improvement and maintenance of the Malabon City Bureau of Fire Protection Stations | Bureau of Fire | Malabon City Fire Station-# 70 Gov. Pascual Ave. Potrero, Malabon City | 4850522.89 | February 14, 2018 | 2022-12-01 | 97.02% | 4706030 |  | Remaining fund balance is P144,492.89, yet to be utilized by BFP-Malabon | date started is the date of receipt
Management and Implementation of the CIPH CY 2014-2015 - "KALUSUGAN PANGKALAHATAN" | DOH-NCR | City Health Department | 805800 | June 25,2020 | 2022-12-01 | 22.06% | 177777.25 |  | Remaining fund balance of P628,022.75, yet to be implemted by City Health Department
Unified Access Quality Tertiary Education Act (UAQTEA) for the Implementation of the approved Qualification Maps (QM) no. 1 & 2 for the free TVET Program of CMPI | DOH-NCR | TESDA-NCR | 914820 | September 2,2019 | January 20, 2020 | 98.43% | 900439.78 |  | the unutilized amount of P14,380.22 was deposited under TESDA acct.# 2812-1022-26 dated 2/18/2022
Implementation of Medical Assistance to Indigent & Poor patients in Government hospitals | DOH-NCR | Ospital ng Malabon | 17850000 | January 2021 | 2022-12-01 | 86.31% | 15405813.97 |  | Ongoing project with available fund balance of P2,444,186.03
Financial assistance to LGU's affected by Typhoon Ulysses | Bureau of the Treasury -NCR | Malabon City | 2061353 | July 15, 2021 | September 9,2021 | 99.04% | 2041487 |  | project completed, the unutilized amount of P19,866.00 was returned to BOT with issued O.R.# 7063423 dated 3/2/2022
Medical assistance for payment of medicines, medical services and other care to indigent patients | Office of the President | Ospital ng Malabon | 16294734.7 | February 05, 2021 | January 26, 2022 | 100% | 16294734.7 |  | project completed, Fund Utilization Report was submitted to the Office of the President last February 3, 2022
2021 Disaster Reduction and Rehabilitation Assistance Program-Financial Assistance for the recovery and reconstruction of economy and livelihood in LGU's affected by Taal Volcano Eruption and Typhoon | Bureau of the Treasury -NCR | Alley bestween Adante & Rivera St. & Drainage | 973439 | July 15, 2021 | September 9,2021 | 99% | 963695 |  | project completed, the unexpended amount of P9,744.00 was returned to BOT with issued O.R.# 7063424 dated 3/2/2022
Nursery and Green Space at Atis Barangay Potrero and Greeening and Beautification of C-4 Raod, Eastment and Sidewalk at Barangay Tañong. | Bureau of the Treasury-NCR | Barangay Potrero | 7337896 | November 15,2021 | February 19,2022 | 74.25% | 5448580.87 |  | 2nd and partial ( 45% ) Payment made under check # 262433 dtd. 2/14/2022
Greeening and Beautification of C-4 Raod, Eastment and Sidewalk at Barangay Tañong. | Bureau of the Treasury-NCR | Barangay Tañong | 10162104 | December 14,2021 | June 11,2022 | 29.69% | 3017276.6 |  | 1st and partial ( 30% ) Payment made under check # 262448 dtd. 3/23/2022
Financial grant for the implementation of "Enhanced Kadiwa ni Ani at Kita Financial Grant Assistance Program. | Department of Agriculture | Nuestra Señora Credit Cooperative & Ang Palengke Natin Service Cooperative at Malabon City | 2000000 | January 26, 2022 | 2022-06-01 | 100% | 2000000 |  | Have released check nos.262415 & 262416 at 1,000,000.00 each, both dated Dec. 31,2021
Financial assistance for the payment of services rendered by the 27 existing Barangay Nutrition Scholars for CY 2021. | National Nutrition Council | Barangay Health Center | 32400 | March 10, 2022 | March 18, 2022 | 100% | 32400 |  | payment made under Report of Disbursement Reference No. 300-2022-003-007 dated March 18, 2022
Meals, accommodations and transportation (MATS) benefits to Public and Private health Care Workers from September 15-December 19,2020 | DOH-NCRO | Ospital ng Malabon | 584500 | March 10, 2022 | March 18, 2022 | 100% | 577500 |  | Fund Utilization Report was submitted to DOH last March 24, 2022. The remaining fund balance of P7,000.00 was returned to DOH with issued O.R. # 2517583 dated 3/24/2022
Medical assistance for payment of medicines, medical services and other care to indigent patients | Office of the President | Ospital ng Malabon | 5000000 | March, 2022 | June 2022 |  | 5000000 |  | with partial utilization, yet to be transferred to General Fund
Grant of ONE COVID-19 Allowance (OCA) for public and private health care workers and non health care workers. | DOH-NCRO | Ospital ng Malabon | 1362750 |  |  |  | 1362750 |  | yet to be utilized
|  |  | 70230319.59 |  |  | 82.48% | 57928485.17
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
MAILA R. CAINGLES |  |  | DINAH A. LAMSEN |  |  | HON. ANTOLIN A. ORETA III
OIC - City Budget Department |  |  | City Accountant |  |  | City Mayor
#REF!
0