## april-june2022
FDPP Form 6 - Trust Fund Utilization
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES
for the 2nd QUARTER, CY 2022
Malabon City
Program or Project | Source Agency | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | Remarks
[6 empty] | % of Completion | Total Cost Incurred to Date
Improvement and maintenance of the Malabon City Bureau of Fire Protection Stations | Bureau of Fire | Malabon City Fire Station-# 70 Gov. Pascual Ave. Potrero, Malabon City | 4850522.89 | February 14, 2018 | 2022-12-01 | 97.02% | 4706030 | Remaining fund balance is P144,492.89, yet to be utilized by BFP-Malabon
Management and Implementation of the CIPH CY 2014-2015 - "KALUSUGAN PANGKALAHATAN" | DOH-NCR | City Health Department | 805800 | June 25,2020 | 2022-12-01 | 22.06% | 177777.25 | Remaining fund balance of P628,022.75, yet to be implemted by City Health Department
Payment for assessment cost` of 25 scholars (Ablay Jomar et al)in RAC Servicing( DomRac) NC II under UAQTEA 2019 | TESDA-NCR | CMPI | 12500 |  | 2022-12-01 |  |  | for payment to concerned scholars
Payment for assessment cost` of 7 scholars (Banaticia Joshua et al) in Tailoring NC II under UAQTEA 2019 | TESDA-NCR | CMPI | 2800 |  | 2022-12-01 |  |  | for payment to concerned scholars
Implementation of Medical Assistance to Indigent & Poor patients in Government hospitals | DOH-NCR | Ospital ng Malabon | 44850000 | January 2021 | 2022-12-01 | 35.1% | 15744550.27 | Ongoing project with available fund balance of P29,105,449.73
Nursery and Green Space at Atis Barangay Potrero and Greeening and Beautification of C-4 Raod, Eastment and Sidewalk at Barangay Tañong. | Bureau of the Treasury-NCR | Barangay Potrero | 7337896 | November 15,2021 | May 5,2022 | 99% | 7264790.66 | Project completed, yet to submit Fund Utilization report to BOT and to return unused amount of P73,105.34.
Greeening and Beautification of C-4 Raod, Eastment and Sidewalk at Barangay Tañong. | Bureau of the Treasury-NCR | Barangay Tañong | 10162104 | December 14,2021 | June 11,2022 | 99% | 10060512.01 | Project completed, yet to submit Fund Utilization report to BOT and to return unused amount of P101,591.99.
Financial grant for the implementation of "Enhanced Kadiwa ni Ani at Kita Financial Grant Assistance Program. | Department of Agriculture | Nuestra Señora Credit Cooperative & Ang Palengke Natin Service Cooperative at Malabon City | 2000000 | January 26, 2022 | 2022-06-01 | 100% | 2000000 | Have released check nos.262415 & 262416 at 1,000,000.00 each, both dated Dec. 31,2021. Fund Utilization Report was submitted last June 10, 2022.
Medical assistance for payment of medicines, medical services and other care to indigent patients | Office of the President | Ospital ng Malabon | 5000000 | March, 2022 | June 2022 | 100% | 5000000 | Fund Utilization Report was already submitted to the Office of the President last June 23, 2022.
Grant of ONE COVID-19 Allowance (OCA) for public and private health care workers and non health care workers. | DOH-NCRO | Ospital ng Malabon | 1362750 | April 20, 2022 | April 28, 2022 | 99.78% | 1359750 | Fund Utilization Report was submitted and the unused amount of P 3,000.00 was returned to DOH under DOH O.R.# 9661624 dated 5/26/2022
Provision of Meals, Accommodations & Transportation benefits from September 15, 2020-December 12-,2020 | DOH-NCRO | City Health Department | 1501500 | April 22, 2022 | May 17, 2022 | 100% | 1501500 | Fund Utilization Report was submitted to DOH last May 20,2022
COVID-19 Special Risk Allowance (SRA) from December 20 to June 30, 2021. | DOH-NCRO | City Health Department | 12488486.5 | 2022-06-14 | June 29, 2022 | 97.6% | 12188717.37 | Fund Utilization Report was submitted and the unutilized amount was returned under DOH OR# 9661905 dated 6/30/2022.
Financial assistance to health sector (OSMAL) development project to assist the government hospital in providinga medical services and support to paupers and prioritize the needs of the underpriveleged, sick ,elderly, disabled as per approved Memorandum dated March 31, 2022. | Office of the President | Ospital ng Malabon | 50000000 |  |  |  |  | For implementation
|  |  | 140374359.39 |  |  |  | 60003627.56
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
MAILA R. CAINGLES |  |  | DINAH A. LAMSEN |  |  | HON. JEANNIE N. SANDOVAL
OIC - City Budget Department |  |  | City Accountant |  |  | City Mayor
0